Environmental and Social Management Plan (ESMP)

Environmental social management plan

FINAL

2022

Table of Contents

Table of Figures	4

1.0 INTRODUCTION	5

1.1 Project Description	5

1.2	Need for the Project	5

1.3 Project Objectives	6

1.4 Project Beneficiaries	6

1.5 Implementation Arrangements	7

2.0 ESMP STUDY METHODOLOGY	7

2.1	Introduction	7

2.2	Literature review	8

2.3	Environmental and Social Baseline	8

2.4	Impact Identification and Mitigation Measures	8

3.0 DESCRIPTION OF THE PROJECT	8

3.1 Project Activities	9

4.0 LEGAL AND POLICY FRAMEWORKS	11

4.1	National Regulatory Framework	11

4.1.1	Constitution of Zimbabwe	11

4.1.2	Environmental Management Act	11

4.1.3	Occupational Health and Safety Act	12

4.1.4	Public Health Act [15:17]	12

4.1.5	Labour  Act	12

4.1.6 Education Ammendment Act (2020)	13

4.2	Policy Framework	13

4.2.1	National Education Policy	13

4.2.2 The Zimbabwe School Health Policy (ZSHP)	13

4.2.3 National Sanitation and Hygiene Strategy	13

4.3	World Bank Environmental and Social Standards	15

4.4	International Conventions	20

5	DESCRIPTION OF THE BASELINE ENVIRONMENT	20

5.1	Location and Size	20

5.2	Physical Environment	21

5.2.1	Water resources and water quality at project locations	21

5.2.2	Solid waste – menstrual waste	21

5.2.3	Payment point security arrangements at project locations	21

5.4	Social, Economic and Cultural Environment	22

5.4.1	Demographics	22

5.4.2	Health	22

5.4.3	Education	22

5.4.4	Land Tenure	22

5.4.5	Economic Activities	22

5.4.6	Sanitation and Wastewater System	22

5.4.7	Telecommunication	23

6.0 ENVIRONMENTAL, SOCIAL IMPACTS AND MITIGATIONS	23

6.1	Project Beneficial Impacts	23

6.2	Project Adverse Impacts	23

6.2.1	Solid waste	23

6.2.2	Air Emissions	24

6.2.3	Impacts on Soils and Water Quality	24

6.2.4	Community Health and Safety	25

6.2.5	Occupational Safety and Health Risks	25

6.2.6	Water resources and water quality	26

6.2.7	Spread of COVID-19 Infections	26

6.2.8	Labor including child labour	27

6.2.9	Gender Based Violence	27

6.2.10	Exclusion of Vulnerable Groups	28

6.2.11 Transparency in Project Benefit Delivery	29

6.3	Environmental and Social Management Plan	30

6.4.1	Project Implementation Unit	36

6.4.2	Organisational Structure/Organogram	37

6.4.3	Zimbabwe Environment Management Authority	37

7.0 STAKEHOLDER ENGAGEMENT AND GRIEVANCE REDRESS	37

Objectives:	38

7.1	Grievance Mechanism	40

7.1.1	Objectives	40

7.1.2	Principles of the GM	40

7.2	Internal Management of the GM	41

7.4	Description of Grievance Mechanism	41

GBV/SEA/SH cases	43

ANNEX 1: LABOUR MANAGEMENT PROCEDURES	45

ANNEX 2:  MENSTRUAL WASTE DISPOSAL GUIDELINES	55

ANNEX 3: Gender Based Violence Action Plan	57

# Table of Figures

Figure 1: Map of Buhera district	19

Figure 2: Blair ventilated pit latrine	22

Figure 3: CIZ Project Organogram	36

Table 1:ESS Applicability	14

Table 2: Environmental and Social Management Plan	29

Table 3: ESMP Implementation plan	35

# 1.0 INTRODUCTION

## 1.1 Project Description

The Piloting Social Protection and WASH Interventions to Keep Adolescent Girls in School in Zimbabwe project aims to test an innovative pilot activity, layering Social Protection and WASH interventions targeting adolescent girls who have been disproportionately affected by coping mechanisms adopted during lockdown, to support their return to school after the several waves of school closure in Zimbabwe. This pilot will directly inform the future policies and programming of the Ministry of Public Service, Labour and Social Welfare (MPSLSW) and other relevant ministries and strengthen their capacities. The pilot will be directly layered over Government’s Basic Education Assistance Module (BEAM) fee waiver program to test whether complementary social protection and WASH interventions are successful in bringing adolescent girls back to school and incentivizing them to stay in school. It will therefore test the effectiveness of complementary measures to the national BEAM program, beyond the fee waiver for vulnerable children, by focusing on gender dimensions and targeting vulnerable adolescent girls within the BEAM caseload. Specifically, the pilot will provide household and school level social protection and WASH support that aim to mitigate negative coping mechanisms that affect adolescent girls, improve access to WASH and menstrual hygiene management, and sensitize households and schools on gender dynamics, GBV, amongst others. The pilot will be overseen jointly with MPSLSW and relevant ministries and knowledge generation and policy dialogue will be undertaken on the findings and recommendations from the pilot towards strengthening government capacity. The pilot will be implemented in Buhera district by Care International Zimbabwe (CIZ), which will build on its existing Start4Girls program to deliver the pilot. Third party implementation will then take place through a subsidiary agreement between Ministry of Finance and CARE International Zimbabwe (CIZ). As such, CIZ will be the implementing agency for the pilot, carrying out the activities described above and supporting the process evaluation and knowledge sharing activities funded under the RSR-18.

## Need for the Project

The impacts of COVID-19 on the Zimbabwe’s poor cannot be underrated and these have been compounded by an underlying economic crisis characterised by hyperinflation and a contracting economy as well as climatic shocks which have adversely affected the poorest in Zimbabwe. For instance, as of April 2021, year-on-year inflation was recorded at 194 percent whilst household final consumption is estimated to have contracted by 12.8 percent due to reduced disposable incomes owing to the negative effects of COVID-19 on the economy.  Under such a context, there is need for both urgent and longer-term support to assist communities to recover and build their resilience as most had resorted to negative coping mechanisms. For adolescent girls, household food and nutrition insecurity, lack of access to menstrual hygiene products, inadequate girl and disability friendly WASH facilities in schools, overwhelming household chores, and harmful gender and social norms such as early marriage and teenage pregnancies have detrimental effects including negative coping strategies and are key barriers affecting their access to education. These have resulted in higher dropout rates, lower school attendance, and lower high school completion rates among girls.

The pilot will test the effect and viability of addressing the needs of vulnerable adolescent girls through strengthening the government’s BEAM fee waiver programme with social protection and WASH interventions. This will contribute towards reducing school dropout among adolescent girls by minimizing barriers that affect regular attendance at school. The interventions will also directly respond to mitigate the impacts of COVID-19 on adolescent girls and their households mitigating negative coping mechanisms that affect adolescent girls, whilst also improving access to WASH and menstrual hygiene management, and sensitizing households and schools on other social dynamics including gender barriers and gender-based violence (GBV), amongst others.

## 1.3 Project Objectives

The project aims to reduce school dropout for adolescent girls resulting from the COVID-19 pandemic, through complementary social protection and WASH interventions in target districts.

## 1.4 Project Beneficiaries

The project will work in secondary schools implementing BEAM, a government supported educational subsidy targeting 30 percent of the vulnerable children enrolled in primary and secondary education in Zimbabwe. The pilot will target households that have at least one adolescent girl under the BEAM program, with interventions at both the household and school levels designed to bring adolescents back to school and keep them in school by reducing negative coping mechanisms leading to dropping out of school and improving access to menstrual hygiene management and WASH in schools. The pilot project will adopt the Inclusive Model of targeting where households must meet all the criterion listed i.e., the residency, eligibility and BEAM participant registration of girl to be eligible. To be eligible, households must have been living in the same catchment area of Buhera for at least six months, which will be verified by the Community Selection Committees, Ward Councillors, and traditional leadership such as the village headpersons. In listing of potential beneficiaries, the pilot will use the Buhera BEAM master lists from schools and district level Ministry of Education with initial screening targeted at picking girls only aged 12 to 19years old.  A Community validation of listed households will ensue. This will entail generated lists of identified potential beneficiaries  being displayed at public places such as community halls, schools and  subjected to a community validation exercise for community participation to determine whether the identified households should proceed for enumeration. The Identification lists will then be ratified by the CSC chairperson, Ward Councillor and the village headpersons and are then submitted to the DSWO who will produce the Enumeration List, which contains the details of households that must be interviewed.

Selected households will receive a package of social protection and WASH hygiene promotion interventions to support girls’ continued education. At the school level, interventions will include sensitization and capacity building for the whole school community including both boys and girls, parents, caretakers, and school staff around gender norms, Sexual and Reproductive Health (SRH), WASH, menstrual hygiene management and positive parenting to foster a more supportive environment for adolescent girls to stay in school.

## 1.5 Implementation Arrangements

In line with the prevailing ZIMREF Trust Fund guidelines for all grants, the Grant Agreement will be signed between the World Bank and Zimbabwe’s Ministry of Finance and Economic Development (MoFED). A Subsidiary Agreement will be signed between MoFED and CARE International Zimbabwe (CIZ) for third-party implementation. As such, CIZ will be the implementing agency for the pilot. The activity will be governed by a Steering Committee and a technical committee comprised of all the above-mentioned stakeholders. The Ministry of Public Service, Labour and Social Welfare (MPSLSW) as well as Ministry of Primary and Secondary Education (MoPSE) will jointly provide guidance and monitoring to pilot activities and knowledge dissemination activities.

The Steering Committee (SC) for the pilot project will be chaired by the PS of MPSLSW and comprised of the Director of Ministry of Finance, CARE’s Country Director and the World Bank’s Country Manager. The SC’s main role is to provide oversight and strategic guidance to the pilot meeting on a quarterly basis. The technical committee will be chaired by MPSLSW and include BEAM program officers, technical staff from MOPSE and Ministry of Agriculture (MoA), CARE technical staff supervising the pilot and the World Bank’s task team leaders (TTLs). This committee will meet on a bi-monthly basis tasked with progress reviews and ensuring stakeholders efficient collaboration on all the project’s technical issues. Further, CIZ staff have the responsibility to coordinate with BEAM structures in the target districts for efficient programme implementation.

A designated focal person for environmental and social safeguards will be appointed within the CIZ. The focal person will support the preparation, implementation, and monitoring of the Environmental and Social Management Plan (ESMP), Stakeholder Engagement Plan (SEP), Grievance Redress Mechanism (GRM) (section 7), Labor Management Procedure (LMP) (Annex 1), and associated plans. Where necessary, CIZ capacity to manage environmental and social risk will be strengthened by hiring a consultant to support the designated environment and social focal point.

# 2.0 ESMP STUDY METHODOLOGY

## 2.1	Introduction

The ESMP preparation followed a typical Environmental Management Act (EMA), 2002 process.  It follows a process of establishing the current baseline conditions, identifying specific environmental and social risks that need to be addressed, characterization of the effects the project will have and the impacts (positive or negative) they will result in, determination of significance of the issues identified, establishment of mitigation measures and monitoring measures, and finally proposals for management plans to ensure effective implementation of mitigation and management of the anticipated issues.

The approach and methodology chosen ensures that applicable World Bank Environmental and Social Standards (ESS), the EMA Environment and Social Impact Assessment (ESIA) processes have been followed. This involved collecting data on the environmental and social situation, conducting consultations with stakeholders and data analysis.

## 2.2	Literature review

This included studying relevant documents including the project proposals and appraisals, legislation, and policies; national and local secondary data sources; and other related reports and documents related to the proposed project including the World Bank safeguards policies on ESIA and associated guidelines.  Key documents reviewed included:

- The Constitution of Zimbabwe

- The Project Environmental and Social Commitment Plan

- Stakeholder Engagement Plan

- World Bank Environmental and Social Framework

- The School Health Policy

- Education Policy

- Environmental Management Act

## 2.3	Environmental and Social Baseline

Environmental and social baseline comprised secondary data collected through review of literature and presented in Chapter 5.

## 2.4	Impact Identification and Mitigation Measures

The primary tool for identification of impacts and mitigation was using expert judgment and consultations including recommendations from stakeholders.  Impacts were identified from the environmental and socio-economic baseline.  Impact assessments were also based on criteria developed from Zimbabwean legal standards and World Bank ESS and discussed in Chapter 6.

# 3.0 DESCRIPTION OF THE PROJECT

The Piloting Social Protection and WASH Interventions to Keep Adolescent Girls in School in Zimbabwe project will test the effect and viability of strengthening the government’s social protection programs, specifically the BEAM fee waiver, with layered social protection and WASH interventions that allow more comprehensive support addressing the needs of vulnerable adolescent girls. The pilot will target BEAM households that have adolescent girls and will work with public secondary schools who benefit from BEAM. The pilot will be implemented by CARE International Zimbabwe (CIZ) which will build on its existing Start4Girls program to deliver the pilot. The pilot will be implemented in Buhera district.  This is a rural district selected for being one of the poorest districts in Zimbabwe and also one of the two districts where CARE’s Start4Girls program is active. This would allow for the pilot to be layered on both the BEAM and Start4Girls program as described and leverage their capacity and reach. The duration of the pilot will be one year. The pilot’s main implementation timeline coincides with the lean season in Zimbabwe (September to March) and as such will be providing support to households during the time they need it most as Buhera is a rural district that is affected by seasonality.

## 3.1 Project Activities

The project will be comprised of two components as follows:

  - Component 1: Household-level Interventions- Cash transfer, Income Generating Activities (IGA), hygiene promotion and menstrual hygiene products: This component will pilot complementary measures to the BEAM fee waiver and will help 400 households in one district, thereby discouraging negative coping strategies that impact adolescent girls and their education, preventing girls from returning to school. Communications with beneficiaries will be very clear regarding the duration of the pilot so that households can plan on the use of their resources.

    - Cash Transfer: The pilot will provide monthly unconditional cash transfers to 400 households with adolescent girls who currently benefit from the BEAM program. The transfer will be paid in monthly instalments equivalent to US$ 35 per household during a six-month period. These multi-purpose cash transfers are meant to help meet basic food and non-food needs of beneficiary adolescent girls and are intended to discourage households from employing negative coping strategies that impact adolescent girls. This is in line with strong evidence that suggests that unconditional cash transfers lead to an increase in school attendance among adolescent girls. For example, a study in rural Malawi showed that the long-term effects of unconditional cash transfers include a delay in marriage and childbearing among school-going adolescent girls. Given that unconditional cash transfers were found to be more effective in Sub-Sharan Africa, the cash transfer will remain entirely unconditional even if adolescent girls in selected households drop out of school.

    - Income Generating Activities (IGA) and capacity building: All households will also receive an IGA livelihoods grant of US$ 250 to fund business plans developed with the support of the pilot through the Start4Girls project. These will be complemented with targeted capacity-building and training focused on business skills, financial literacy, etc. Given the rural focus of the pilot, the project expects to support activities such as small livestock rearing, gardening and petty trading. The aim is for households to strengthen their income generation activities through these grants past the duration of the pilot to ensure sustainability of the intervention. A study of 6 countries shows the combination of IGA grants and coaching produces long-lasting impacts on beneficiaries’ livelihoods, earnings, consumption, and psychosocial health, two years, four years, and seven years after the intervention. Also, emerging evidence from Burundi, Afghanistan, and Bangladesh suggests significant educational and health improvements for children of beneficiaries of productive inclusion (IGA) programs.

    - Strengthen water-related hygiene behavior: the focus will be on awareness of safe sanitary practices for all target households. This will help ensure that households’ WASH understanding is enhanced and improved, through raising awareness and practicing sound hygiene practices, such as handwashing with soap and improved menstrual hygiene practices, targeted at adolescent girls. Additionally, the households and schools will receive support and training for the use of water purification tablets to mitigate water quality risks at school and in households. This component is particularly key given the COVID-19 context and will reinforce WASH messaging on hand washing and other practices delivered through schools.

    - Provision of Menstrual Hygiene kits: Evidence suggests that a lack of menstrual hygiene products impacts girls’ school attendance, hence, this activity is essential to combating school dropout among adolescent girls. The pilot will deliver menstrual hygiene kits to girls in the cash transfer households.

  - Component 2: School-level Interventions- Sensitization, Capacity Building and WASH Promotion: This component will work closely with public secondary schools receiving BEAM support to test the promotion of positive gender norms, sexual and reproductive health messaging, good hygiene, and menstrual hygiene management including raising awareness among adolescent girls. Research , for example in Bangladesh, found that awareness raising and sensitization activities targeting adolescent girls significantly improve their likelihood of attending school 18 months after the intervention.

    - Sensitization and capacity building meetings: The pilot will organize sensitizations and capacity building meetings covering two main areas. The first will be bi-weekly sensitization and capacity building meetings held in schools at a date and time chosen collectively by students targeting boys and girls at school, as well as their parents, where appropriate. Parent’s consent will be sought. These sessions will aim to mitigate negative coping strategies, adopted in times of domestic economic hardships where households forgo nutritional, hygiene and other needs resulting in prioritization conflicts amongst household members. Domestic violence usually follows where there are conflicts and disagreements over prioritization and address of these household needs. The project will facilitate capacity building sessions on positive parenting and saving to direct funds towards the support of the girl child. Sessions focusing on gender dynamics will touch upon sexual and reproductive health (SRH), gender-based violence (GBV), and menstrual hygiene management, among others. For sessions focusing on menstrual hygiene and WASH, proven behaviour changes and health promotion techniques will be used to raise awareness on healthy menstrual hygiene practices and advocating for improved adoption of healthy personal hygiene practices including handwashing. Resources such as the Global Handwashing Partnership will be tapped into for development of information and communication materials for dissemination of messages. School level mass awareness sessions will complement the provision of menstrual hygiene kits, educational material, and cleaning of school WASH facilities.

    - Promoting WASH at public secondary schools: There will also be bi-monthly meetings for school staff focusing on WASH. Sessions for school staff will focus on gender responsive education and girl friendly WASH and menstrual hygiene management and will also employ the above-mentioned resources. Evidence from Bangladesh suggests that school-based sensitization on menstrual hygiene improved knowledge and behaviors on menstrual hygiene management among adolescent girls and reduced hygiene-related complications

# 4.0 LEGAL AND POLICY FRAMEWORKS

## 4.1	National Regulatory Framework

In this section, relevant Zimbabwe regulations and policies that guide the environmental and social management plan for the CIZ activities will be summarised including the relevant World Bank Environmental and Social Standards,  WHO Guidelines for drinking water quality and other relevant international conventions. The objective is to ensure that project activities and implementation processes are consistent with local laws and policies and World Bank Standards, and to point out possible gaps in local legislation in view of full compliance with World Bank standards.

### Constitution of Zimbabwe

The Constitution of Zimbabwe (2013) is the overall guiding document which  informs all local laws and policies and guides all citizens’ rights. The Constitution provides for the right to education for all children [Section 75] and provides for “free and compulsory basic education for all children” . Section 56 of Constitution, provides a strong framework for the protection and promotion of the rights of women and men, girls and boys in Zimbabwe. It recognises the equality of all persons and goes further to explicitly outlaw discrimination on the grounds of sex or gender. Section 29(1) and (3) in the National Objectives in the Constitution, obliges the State to take all practical measures to ensure the provision of basic, accessible and adequate health services throughout Zimbabwe; and take all preventive measures within the limits of the resources available to it, including education and public awareness programmes, against the spread of disease.

### 4.1.2	Environmental Management Act

The Environmental Management Act, Chapter 20:2 and the accompanying Regulations and the Environmental Impact Assessment Guidelines, 1997 form the legislative and policy framework guidelines for environmental management in Zimbabwe. The Environmental Management Act (EMA), 2002 forms the basis for all Environmental Management in Zimbabwe. The Act repeals the Natural Resources Act, Chapter 20:13, the Atmospheric Pollution Prevention Act, Chapter 20:03, the Hazardous and Articles Act, Chapter 15:05 and the Noxious Weeds Act. The Act translates the Environmental Policy Guidelines proposed in 1997 into a legally binding requirement for all specified developments under Part XI, section 97 and listed in the First Schedule, of the EMA. These include tourism developments. Failure to undertake an EIA for specified developments becomes an offence. The proponent becomes liable to pay a penalty or face 5 years imprisonment (Part XI, section 97, EMA, chapter. 20.27). This ESMP is in fulfillment of section 97 of the Act. Section 106 of EMA (1) provides for the Environmental Management Agency to carry out periodic environmental audits on any projects for the purpose of ensuring that their implementation complies with the requirements of the Act.

Section 107 (1) states that “every developer shall take all reasonable measures to prevent or if prevention is not practicable to mitigate any undesirable effects on the environment that may arise from the implementation of his project” – To this end, this ESMP report contains an Environmental Management and Monitoring Plan aimed at mitigating and managing potential environmental and social impacts resulting from the proposed development.

The Zimbabwe Environmental Management Act (13/2002, 5/2004, 6/2005) requires environmental impact assessments for specific types of Projects (97). Assessment proposals need to lay out the methodology for the assessment. The assessment results are submitted to the Director-General of the Environment Management Board may consult any authority, organization, community, agency or person that he considers may have an interest in the Project (100 (2)(c)).

### 4.1.3	Occupational Health and Safety Act

Occupational safety and health in Zimbabwe is regulated generally by the Factories and Works Act (20 of 1948), the Labour Act , the National Social Security Authority (Accident Prevention and Workers Compensation Scheme) Notice No. 68 of 1990 and the Labour Relations (HIV and AIDS) regulations S.I.202 of 1998. This Act provides for the protection against risks to health or safety arising from, or in connection with, the activities of persons at work. It specifically provides for the regulation of conditions of work, supervision of the use of machinery, precautions against accident to persons employed on structural work  and the compensation of employment-related injuries and diseases. It also provides for the workers’ responsibility for their personal health and complying with the provisions of the Act.

### 4.1.4	Public Health Act [15:17]

The Act makes provision for the control of activities and situations that have potential to affect public health. It establishes powers of health officials, local authorities and has several regulations made subservient to it, including the Public Health (Effluent) Regulations 1972 (SI.639 of 1972) which serves to control the disposal of waste into the environment. This Act also has sections which deal with emergency situations, epidemics, etc. such as COVID-19. The Publich Health Act defines a child as anyone under the age of 18 years, and states that “informed consent” can only be given by a person who has legal capacity to do so. The Act is silent on sexual and reproductive health services, which leaves the provision of such services to children unclear and up to the health care worker to interpret whether or not a child can receive such services without a guardian present. There is need to amend the Act to ensure adolescents can access sexual health services universally.

### 4.1.5	Labour  Act

The Act declares and defines the fundamental rights of employees in Zimbabwe and regulates conditions of employment (including issues relating to occupational safety and health).  in line with the  International Labour Organisation and other internaltional governing conditions of employment that Zimbabwe has ratified. The Act serves to define unfair labour practices; regulate conditions of employment and other related matters; provide for the control of wages and salaries; to provide for the appointment and functions of workers committees; provide for the formation, registration and functions of trade unions, employers organizations and employment councils; regulate the negotiation, scope and enforcement of collective bargaining agreements. It also provides for the prevention of trade disputes, and unfair labour practicesas well as  regulating and controlling collective job action.

### 4.1.6 Education Ammendment Act (2020)

The Act is aligned with the Constitution and declares every citizen’s right to basic state-funded education from early childhood up to the fourth form where pupils will not be required to pay fees or levies, with the state comiitting to  providing all learning and teaching material. Section 4 of the Act declares that the State must ensure provision of sanitary ware and other menstrual health facilities to girls in all schools to promote menstrul health. It also provides for the appointment of a sexual and reproductive  health personnel at every school.  The Act also states the importance of basic education for every child, making it an offense for any parent/guardian who deprives their child the right to basic state funded education. Section 64 (1), stipulates that the Minister of Primary and Secondary Education in consultation with the Minister responsible for Health shall make regulations for the purposes of safeguarding the health of learners.

## 4.2	Policy Framework

### 4.2.1	National Education Policy

In 2020, GoZ adopted the Education Amendment Act which has fairly extensive provisions to protect, respect and fulfil the right to basic education for all children and addresses issues pertinent to the girl child, including the prohibition of expelling pregnant girls from school, promoting sexual reproductive health and rights and menstrual hygiene management provisions. Moreover, since 2001, GoZ has implemented the nationwide Basic Education Assistance Module (BEAM) social protection program, which covers school and examination fees and levies to support the education of orphaned and vulnerable children aged 4-19 years old including learners with disabilities. While the national policy is that there are no compulsory fees, Government has promulgated a policy position which prevents schools from refusing access to students who do not pay levies or other fees.

### 4.2.2 The Zimbabwe School Health Policy (ZSHP)

The ZSHP aims to promote positive health determinants while preventing and mitigating health risks among learners through provision of equitable, sustainable and quality health services for all learners. It provides a broad frame of reference to guide the implementation of a number of health related issues relating to the welfare of learners in the school system, such as health and nutrition, education services, water, sanitation and hygiene, needs of learners with disabilities, mental health, sexual and reproductive health concerns, the care and support provisions as well as guidance and counselling needs of all learners.  Though the policy mentions reproductive health it does not refer specifically to menstruation and MHM. Sexuality and HIV/AIDS related topics are part of the multipronged approach of providing guidance and counselling as a learning area.

### 4.2.3 National Sanitation and Hygiene Strategy

Zimbabwe's National Action Committee on Water, Sanitation and Hygiene has a sanitation and hygiene strategy which puts in place key measures for sustained sanitation and hygiene service delivery in Zimbabwe to eliminate open defecation and other related ills. WASH has helped to combine Zimbabwe’s urban and rural sanitization efforts to gain a more organized action plan on how to improve sanitation, restore leadership throughout urban and rural areas, institutionalize Government responsibilities and support sector development.

### 4.2.4 WHO Guidelines for drinking water

The Guidelines cover a large number of potential constituents in drinking-water in order to meet the varied needs of countries worldwide, acknowledging that only a few constituents will be of public health concern under any given circumstances. Health-based targets are established for potentially hazardous water constituents and provide a basis for assessing drinking-water quality. Different parameters may require different priorities for management to improve and protect public health. In general, the priorities, in decreasing order, are to:

- ensure an adequate supply of microbially safe water and maintain acceptability to discourage consumers from using potentially less microbially safe water;

- manage key chemical hazards known to cause adverse health effects;

- address other chemical hazards, particularly those that affect the acceptability of drinking-water in terms of its taste, odour and appearance;

- apply appropriate technologies to reduce contaminant concentrations in the source to below the guideline or regulated values.

The two key features in choosing hazards for which setting a standard is desirable on health grounds are the health impacts (severity) associated with the substance and the probability of significant occurrence (exposure). The Guidelines encourages the development of water safety plans, operational monitoring which is usually carried out through simple observations and tests, in order to rapidly confirm that control measures are continuing to work and to ensure that health-based targets are met. The WHO Guidelines also encourages  verification of the drinking water quality which is the use of methods, procedures or tests in addition to those used in operational monitoring to determine whether the performance of the drinking-water supply is in compliance with the stated objectives outlined by the health-based targets and whether the WSP needs modification or revalidation.

## 4.3	World Bank Environmental and Social Standards

In addition to the national policy and legal framework, this ESMP takes into consideration the World Bank applicable Environmental and Social Standards (ESS).  The table below lists the ESS that are applicable to this project.

Table 1:ESS Applicability

| Environmental and Social Standard | Applicability |
| --- | --- |
| ESS1: Assessment and Management of Environmental and Social Risks and Impacts | There are key social and environmental concerns applying to the project and some have already been mitigated as articulated in the Stakeholder Engagement Plan including (1) exclusion of vulnerable groups, and other rural and marginalized groups who will not be directly targeted by the project; (2) risk of misinformation about eligibility criteria and local conflict over cash transfer challenges, (3) fraud and corruption to influence enrolment into the cash transfer intervention . The ESMP outlines the remaining concerns and mitigation measures around (1) risk increase in GBV/SEA/SH incidents over use of cash transfers and IGA grants (2) increase of and project constraints by COVID-19 and (3) environmental pollution caused by improper disposal of menstrual hygiene waste. The ESMP outlines in detail the environmental and social management issues including menstrual waste management and use of purification tablets. All consultants engaged by the project shall receive training on OHS. As committed in the ESCP, the environment and social risks of the project will be managed by a designated focal person (an environmental and social safeguards specialist) within the PIE, who will be supported or trained by the World Bank’s environmental and social specialists. There will be no construction activities, occupation of land and, therefore, the project will not directly impact on biodiversity conservation or interfere with sustainable management of living natural resources or will have a direct impact on tangible or intangible cultural heritage. |
| ESS2 Labor and Working Conditions | The project workforce is expected to include direct workers only: CIZ staff, and a small number of consultants engaged directly by the CIZ (i.e. Consultancy on strengthening the enabling environment for improved, gender-balanced WASH at schools). The CIZ shall ensure all project workers are trained on GBV/SEA/SH risks and sign the codes of conduct before starting work on any project activities. These project workers will utilize the existing CIZ grievance mechanisms. The existing mechanism meets ESS2 requirements as set out in para 21-23 of the ESF. The mechanism will receive complaints of a sensitive nature, including with respect to GBV/SEA/SH on a confidential and anonymous basis. Where government civil servants (i.e. Ministry of Public Service, Labour and Social Welfare, Ministry of Primary and Secondary Education, Ministry of Environment, Water and Climate and Ministry of Finance) are involved with the project, this will be only in an oversight and coordination capacity rather than any direct implementation. Whether full-time or part-time, they will remain subject to the terms and conditions of their existing public sector employment agreement or arrangement. ESS2 will not apply to such government civil servants, except for the provisions of paragraphs 17 to 20 (Protecting the Work Force) and paragraphs 24 to 30 (Occupational Health and Safety), which fall under the provisions for workers' safety, as outlined in ESS 2. The OHS measures that apply to the project will be set out in the legal agreement, the ESMP, and the ESCP. The key risk for project workers is COVID-19 transmission. Project activities at the household and school level and stakeholder engagement activities may increase the risk of transmission of COVID-19, hence, according to the ESCP, a COVID-19 safety protocol has been developed as part of the ESMP ( see Annex 4) In accordance with ESS2 and Zimbabwean law, children under the age of 18 will not be allowed to work on the project. The use of forced labor or conscripted labor on the project is also prohibited. The CIZ through the ESCP has committed to the preparation of a LMP( see Annex 1 ) which will i) respond to the specific health and safety issues posed by COVID-19, ii) protect workers’ rights as set out in ESS2 and outline the workers GM, and iii) prevention of GBV/SEA/SH. |
| ESS3 Resource Efficiency and Pollution Prevention and Management | ESS 3 requires the avoidance of the release of pollutants to air, water and land, control of the concentration and the use of applicable WB guidelines and standards. In this project, this will entail waste management guidelines for the school and home environment following the protocol of reduce and reuse to adopt a sustainable and pollution prevention approach. This will influence the selection and use of menstrual materials and products including measures to dispose of waste menstrual material using an acceptable method that conforms to ESS 3. For Water Quality Management, the project will implement training guidelines for the use of water purification tablets to support menstrual management and the use of safe water for infection prevention. |
| ESS4 Community Health and Safety | The main risks identified at this stage include the risk of conflicts and disagreements over the use cash transfer and project grants. Given the domestic economic hardships in the country, one negative coping mechanism may be to forgo nutritional and hygiene needs, and, therefore, conflicts and disagreements over the prioritization of households’ needs may occur among household members. There is also the risk of GBV/SEA/SH from intimate partners, community members or project workers during both the household and school-level interventions, due to the contextual risks of GBV in Zimbabwe. These GBV/SEA/SH risks will be managed through measures included in the ESMP. Furthermore, the project activities at community level may increase the risk of COVID-19 transmission, and as such, a COVID-19 safety protocol has been developed as part of the ESMP as required under the ESCP within 45 days of project effectiveness and shall be implemented throughout the project. In addition, the project will ensure that grievances, including those relating to GBV/SEA/SH, are received, handled, and directed to appropriate services consistent with Bank guidelines in relation to these matters. The GRM procedures are outlined in the SEP. Further, Component 2 capacity-building activities explicitly address gender inequalities and GBV in program participation. The capacity-building activities focus on gender dynamics, sexual and reproductive health (SRH), GBV, gender-responsive education, and girl-friendly WASH and menstrual hygiene management. The LMP outlines the code of conduct for project workers to prevent GBV/SEA-H. There are also security (such as theft and violence) and occupational health and safety risks associated with the beneficiaries of the cash transfers and small grants. To minimize chances of security risks related to handling cash payments and to mitigate Covid-19 transmission during cash-outs, as much as is possible the pilot project will use digital services for beneficiary cash transfer payments. These risk control measures is articulated in the project’s ESMP ( see section 6.2.4) |
| ESS5 Land Acquisition, Restrictions on Land Use and Involuntary Resettlement | ESS 5 is not currently relevant to the project, as no land acquisition, restriction on land use and involuntary resettlement is anticipated. |
| ESS6 Biodiversity Conservation and Sustainable Management of Living Natural Resources | ESS 6 is not relevant at this time as project will not impact on biodiversity conservation and sustainable management of living natural resources. |
| ESS7 Indigenous Peoples/Sub-Saharan African Historically Underserved Traditional Local Communities | ESS7 is not considered relevant to this project as there are no distinct social and cultural groups in the project area that exhibit characteristics of indigenous or traditionally under-served communities as spelled out under this standard. Should a subsequent screening process indicate that a particular group meets the requirements of ESS7 and will be impacted by this project, a social development plan which accords with this standard will be developed. |
| ESS8 Cultural Heritage | ESS 8 is not currently relevant to project. Since there is no land use or involvement of any community there will be no impact on tangible or intangible cultural heritage |
| ESS9 Financial Intermediaries | ESS 9 is not currently relevant to project as there will no financial intermediaries involved. |
| ESS10 Stakeholder Engagement and Information Disclosure | The project adopted a Stakeholder Engagement Plan (SEP), prepared by CIZ. The SEP provides a comprehensive programme for stakeholder engagement with timely, relevant, understandable and accessible information, and consultations in a culturally appropriate manner, which is free of manipulation, interference, coercion, discrimination and intimidation. Information sharing and stakeholder consultations are aimed at dispelling false information about the pilot program, particularly with regards to the cash transfer and grant scheme, as well as providing a transparent, effective and responsive mechanism for stakeholders to lodge grievances, including those of sensitive nature. Sensitive issues include incidents of GBV/SEA/SH, corruption, fraud and other integrity and accountability issues. Preliminary stakeholder mapping has been conducted. Parties affected by the project were identified as adolescent girls and boys; parents/guardians and households with adolescent girls; BEAM school staff; BEAM community selection committees; local leadership. Other interested parties include the District Development Coordinator; the Buhera District Council, MOHCC. MOWACDSME, press, NGOs and media and general public. The SEP will be continuously updated during project implementation. The SEP addresses specific risks identified by stakeholder category and their communication needs as well as strategies for consultations at each stage on specific topics. Vulnerable groups have been identified as well as approaches to incorporate their view in light of existing gendered power imbalances. The SEP also outline the existing CIZ grievance mechanism that will be used by the project to enable stakeholders to raise project related concerns and grievances. |

## 4.4	International Conventions

Zimbabwe is a party to many international and regional conventions aimed at addressing social protection and access to education. Those relevant to the proposed project include but not limited to:-

- United Nations Convention on the Elimination of Discrimination Against Women

- United Nations Convention on the Rights of the Child (CRC)

- International Covenant on Economic, Social and Cultural Rights

- International Labour Organization (ILO)

# 5	DESCRIPTION OF THE BASELINE ENVIRONMENT

## 5.1	Location and Size

The project will be implemented in Buhera, a rural district in Manicaland Province, Zimbabwe. The district lies about 170 km southwest of Mutare, the provincial capital of Manicaland. It is situated between latitude 19degres 19 South and altitude 31degrees 32 East at an altitude of 1190m. The district is served by three designated growth points namely Murambinda, Buhera and Birchenough.  Christianity and traditional practices are predominant in the district with a significant proportion of the population belonging to apostolic sects (such as Johanne Marange, African Apostolic, Zion, Jekenishini).

Figure 1: Map of Buhera district

## 5.2	Physical Environment

The highest mountain in Buhera is the Maremare Mountain near Mutiusinazita service Centre in Buhera South. Buhera district has a generally flat terrain but has poor road networks mainly dusty rocky granite and under serviced gravel roads thus posing accessibility challenges amongst its populace to essential services such as health, education, and urban growth points. The district which is mainly rural in nature lies between the save valley(river) from the north to the south-east and the Devure-Nyazvidzi river on the southwestern side. Most of the vegetation has been cut down for communal cultivation purposes while the hills and stream banks have retained some substantial amount of vegetation.

### 5.2.1	Water resources and water quality at project locations

The district is characterized by unreliable rainfall and is classified under agro-ecological region 3;4 and 5(dry farming regions) with an average annual rainfall precipitation rate of 780mm and average highest temperatures of 30 degrees in summer and lowest of 8 degrees in winter. The semi-arid agro-climate and erratic rainfall results in water scarcity and low groundwater levels within the district. The major source of drinking water in Buhera district is from ground water via borehole bush pumps in the schools whilst at household level the most common water sources (27%) are from unimproved water sources such as unprotected deep wells and shallow wells. During dry spells, some households will resort to fetching water from shallow unprotected wells and perennial rivers. Groundwater which is the main source of drinking water in the district is characterized by high levels of turbidity. It is assumed the water used for menstrual hygiene will contain high levels of turbidity which could imply high concentrations of pathogens (bacteria, viruses and protozoa).  Fecal coliforms have been detected in the likely sources of water within the district such as boreholes, unprotected shallow wells and deep wells. In terms of menstrual hygiene practices it will be critical to filter the water and add chlorine tablets using the correct dosage to kill the pathogens to prevent menstrual hygiene related infections.

### 5.2.2	Solid waste – menstrual waste

The project site is characterised by Blair latrines (described in section 5.4.6 below) both at the schools and household level for menstrual hygiene waste and human waste disposal. Menstrual waste is disposed of in Blair pit latrines as they are the easily available ways of disposing human waste and other bio degradable human waste such as sanitary ware. The Blair pit latrine also provide a space for changing and disposing used menstrual ware. Schools and community households also use refuse pits for disposal of other mixed  biodegradable and non-biodegradable domestic waste such as waste from everyday house-cleaning, paper and non-biodegradable scrap metals.

### 5.2.3	Payment point security arrangements at project locations

The project will use mobile money platform, mainly Ecocash. A database will be sent to the mobile money service provider and they will assist with registration of all beneficiaries and supply them with Econet lines. Econet has excellent network coverage in the area and Ecocash merchants in the district.  Econet as a service provider of Ecocash mobile money has nationally approved organisational security systems in place. Project beneficiaries will be sensitised on security awareness once they receive their cash out.

## 5.4	Social, Economic and Cultural Environment

### 5.4.1	Demographics

According to the 2012 census, the district is estimated to have a population of 245,878 people (with 46,4% being males and 53,6 being females).

### 5.4.2	Health

The district is serviced by two main hospitals, Murambinda Mission hospital  and Birchenough Bridge government hospital. Murambinda hospital is administered under the Ministry of Health and owned by the Roman Catholic Sisters of the Little Company of Mary. a referral centre of 33 rural health centers in the district. It receives financial support from Friends of Murambinda, a UK registered charity organisation. The hospital has 200 beds and professional staff l including: 4 physicians/surgeons, and a number of nurses and midwives.

### 5.4.3	Education

The district boasts of a total of 143 primary schools and 73 high schools including two  boarding schools namely Nyashanu and Makumbe Mission high schools. The literacy rate for Buhera district stands at 95% the second lowest in the Province where Chipinge possess the lowest of 93% and Mutare and Rusape boasts of highest literacy rates of 99%.

### 5.4.4	Land Tenure

The district is characterised by 82% communal land ownership controlled by traditional leadership (chiefs and headmen). It has three growth points on Buhera rural district lease ownership namely Murambinda, Birchenough bridge and Buhera growth points.

### 5.4.5	Economic Activities

The district’s local economy mainly depends on subsistence farming with maize, millet, roundnuts and groundnuts as the main crops produced. Horticultural farming and cattle ranching are also practiced for income generation albeit at subsistence level. Although most people rely on informal petty trading for a living, the largest employer in the district is the Dorowa Minerals, a phosphate mine, which employs 300 people.

### 5.4.6	Sanitation and Wastewater System

The schools and 90 % of the households are dependent of onsite sewerage waste systems mainly Blair ventilated pit latrines. Blair latrines are latrines constructed on brick lined pits where human waste is safely disposed of, and it is the most recommended means of sewage(human) waste disposal in rural Zimbabwe where most households are not connected to piped water and sewerage systems. Growth points which are centres of urban growth are characterised by modern buildings serviced with piped water and connected to piped off-site solid and liquid wastewater sewerage reticulation systems.

Figure 2: Blair ventilated pit latrine

### 5.4.7	Telecommunication

Mobile communication is the main means of communication with the area serviced by all the major network providers in Zimbabwe. Net one dominates, followed by Econet and less of Telecel. Percentages of coverage will be illuminated through the baseline.

# 6.0 ENVIRONMENTAL, SOCIAL IMPACTS AND MITIGATIONS

### 6.1	Project Beneficial Impacts

The project will generate direct positive social and environmental impacts. Positive social impacts will entail provision of menstrual hygiene kits which are expected to help improve school attendance, retention and transition for adolescent girls. Livelihoods strengthening for households to support adolescent girls’ education. Adolescent girls will directly benefit from improved knowledge on SRH and menstrual hygiene practices whilst communities will also be impacted through positive changes in knowledge, attitudes and behaviours on gender norms, parenting, WASH and fostering a more supportive environment for girls’ education. The project is also likely to strengthen the participating line Ministries capacities in developing evidence informed policies whilst schools staff will have increased knowledge on basic concepts of WASH and menstrual hygiene. Positive environmental impacts will include water treatment and ensuring proper disposal of menstrual hygiene products.

## 6.2	Project Adverse Impacts

### 6.2.1	Solid waste

Though provision of menstrual hygiene material is positive, there is a risk of pollution with this solid waste due to lack of information on the correct hygienic and environmental management of menstrual hygiene waste resulting in inappropriate disposal in the environment, in pit latrines and in household solid waste. Other menstrual hygiene waste disposal practices include improper burial, burning, disposal in water bodies causing environmental pollution and associated health hazards. Commercial disposable sanitary pads are typically composed of bleached cellulose, super absorbent polymers (SAPs) and non-biodegradable synthetic fibres. Menstrual hygiene waste can decompose in pit latrines; however, those with plastic inlays are not easily biodegradable.

### 6.2.2	Air Emissions

Negative impact on air emissions could result from open burning and improper incineration of menstrual hygiene waste. Incineration could be used to dispose of menstrual waste, but it is highly likely this will become open burning and it is not appropriate for this project. Burning of pads releases harmful gasses that affects health and the environment. Burning of inorganic material at low temperature releases dioxins which are toxic and carcinogenic in nature.

### 6.2.3	Impacts on Soils and Water Quality

Where menstrual hygiene sanitary pads are inappropriately disposed of i.e., burial, the plastic inlay are not biodegradable and if deodorized, sanitary products contain chemicals used in bleaching such as organochlorines which when buried in the soil disturb the soil microflora prolonging decomposition. Menstrual hygiene waste products soaked with blood of a hepatitis or HPV infected girl adolescent contain active viruses which retain their infectivity and live up to six months in the soil.  Throwing used menstrual hygiene waste in open water sources further pollutes the unprotected water bodies by contaminating water and as debris along rivers. Studies suggest that disposable menstrual products based on rayon and cotton have an acidification and eutrophication environmental impacts, possibly the same impact as plastics.

Mitigation Measures on Menstrual Hygiene Waste

- The provision of menstrual waste collection bins in schools.

- The project will procure and distribute biodegradable menstrual hygiene products to all project participants.

- The project will introduce and trial the use of reusable menstrual pads

- Educate and sensitize on proper disposal of biodegradable menstrual hygiene waste. In a rural setting like Buhera with limited access to water, use of compostable sanitary pads made of natural fibres is recommended. These can be disposed in pit latrines.

- Deep burial will be used for biodegradable menstrual hygiene waste by digging a burial pit, which should be covered with soil or sand. It should not be kept exposed to open air and should be constructed at about 5 to 7 meters horizontal distance from any drinking water source with minimum specifications of 0.5 m(L) × 0.5 m(W) × 1.0 m(D), or 1.0 m(L) ×1.0(W) x 1.0. (D) as well as at least 2 meters from the groundwater source to minimize microbial contamination ( see Annex 2)

- In the event disposable sanitary wear is provided then the waste will be collected by the local authorities from the menstrual waste bins at the schools and transported to the local healthcare facility for co-disposal within the facilities healthcare waste.

### 6.2.4	Community Health and Safety

There are risks related to spread of COVID-19 as some project activities requires face-to-face interactions especially during meetings and trainings. Also, gender-based violence, mainly intimate partner violence can be triggered by conflicts over management of the grants within households especially with women as the ones collecting the funds and with limited power over resource control in household. Violence may also occur during or in transit to other activities like capacity building meetings.  There is potential for conflicts arising due to misunderstandings in cases where households will be using an alternate due to lack of identification documents for registration on the mobile money platform. Thefts may also occur targeted at beneficiaries especially after receiving their cash transfers or the small grants. Disgruntlements over the selection process for the small grants between eligible and ineligible people are a possibility. There is the potential risk of misinformation spreading through communities, local media and social media about the eligibility criteria and anticipated benefits from the pilot project. As this pilot is layered over the BEAM program, which is nationwide, all current BEAM beneficiaries may assume they are eligible to benefit from the pilot leading to a rise in grievances around the administration of the project.

Mitigation Measures

- The implementation of the Stakeholder Engagement Plan (SEP) is the primary mitigation measure for addressing the risk of misinformation through sharing information and undertaking meaningful consultation regarding the pilot project.

- Information about the pilot will be disclosed through social media, and the local media

- Beneficiaries and the public can also access information, raise questions, and file grievances through community level established community grievance mechanisms channels.

- COVID-19 safety protocol was developed as part of this ESMP and will be implemented throughout the project  and includes  project staff, project beneficiaries, stakeholders and partners (Annex 4).

- Encourage beneficiaries to use different mobile money pay points to avoid being targeted by thieves, having established their monthly cash-out routine.

- Setting up and roll out of a GBV sensitive GRM (see Section 7.1), including extensive sensitization and awareness raising efforts in the community.

- GBV action plan(see Annex 3).

- Component 2 capacity-building activities will explicitly address gender inequalities and GBV in program participation. The capacity-building activities will focus on gender dynamics, sexual and reproductive health (SRH), GBV, gender-responsive education, and girl-friendly WASH and menstrual hygiene management.

- To minimize chances of security risks related to handling cash payments and to mitigate Covid-19 transmission during cash-outs, as much as is possible the pilot project will use digital services for beneficiary cash transfer payments.

- The LMP prepared as part of this ESMP outline the code of conduct for project workers and security personnel to prevent GBV/SEA-H.

6.2.5	Occupational Safety and Health Risks

There is also potential risk of exposure  to contaminated water and surfaces . For staff in the project, there is risk of sexual harassment for both female and male staff as well as consultants and civil servants staff participating in the project.

Mitigation Measures:

- Sensitization trainings provided to those handling menstrual hygiene waste on how to handle menstrual hygiene waste for disposal so that they are not exposed to pathogenic organisms.

- Water filtration using a cloth

- Use of chlorine tablets for water treatment to kill micro- organisms in water to prevent cholera, typhoid, dysentery and other water borne diseases and disinfection of working surfaces.

- Ensuring all project participants abide to a GBV/SEA-H code of conduct which they will be oriented on and sign against.

- Cashing out from centrally located pay points/banks with improved security in cases where project participants may need cash and alternatively arranging for localized transactions using ECOCASH mobile money transfer platforms.

### 6.2.6	Water resources and water quality

The major source of water for menstrual hygiene practices in the area are  from boreholes, unprotected shallow wells and deep wells.  As mentioned, potential water sources could be contaminated with pathogens.. Urinary Tract Infections (UTIs) occur mainly in women and affect the bladder and urethra. This type of UTI is usually caused by Escherichia coli (E. coli), a type of bacteria commonly found in the gastrointestinal (GI) tract. However, sometimes other bacteria are responsible.

Mitigation Measures:

- Promote use of safe water sources such as protected deep and shallow wells and boreholes.

- Filter water using a cloth before chlorination.

- Chlorine tablets supplier treatment guidelines/instructions will be adopted, along with training, prior to distribution of chlorine tablets to households.

- All targeted households will be provided with chlorine tablets to purify their water.

- Each household will be supplied with a month’s supply of the Chlorine tablets based on the household size and the Sphere Standards minimum drinking water standards which estimates that a person will use a minimum of 15 litres per day.

- Using the participatory health and hygiene education (PHHE) approach, households will be educated and offered trainings on water quality and purification needs including boiling and encouraged to adopt simple and easy behaviors to protect and improve the quality of their water supplies.

- Sterilization of water by boiling. (i) If water is cloudy, let it settle and filter it through a clean cloth (ii) Bring water to a rolling boil for at least one minute. At altitudes above 5,000 feet (1,000 meters), boil water for three minutes (iii) Let water cool naturally and store it in clean containers with covers.

- Households will be encouraged to use narrow mouthed containers with lids to minimize chances of contamination during transportation and storage.

### 6.2.7	Spread of COVID-19 Infections

Project activities at the household and school levels as well as stakeholder engagement activities may increase the risk of transmission of COVID-19  transmission between and amongst project workers and the beneficiary communities as people will be gathering in significant numbers.  COVID-19 infections may spread due to weak compliance with the precaution measures for infection prevention and control especially during sensitisation and capacity building meetings.

Mitigation Measures:

Households and schools should establish and apply standard precautions including:

- Hand hygiene and use of personal protective equipment (masks );

- Maintain social distance protocols while participating in project activities requiring face to face interactions.

- Conduct trainings and meetings in open spaces.

- Provision of adequate and required personal protective equipment (PPE) to project officers and ensuring all project participants adhere to COVID-19 prevention protocols.

### 6.2.8	Labor including child labour

Poor labor and working conditions may impact adversely on the workers in the project.  Impacts may include  gender based violence and/or sexual exploitation, abuse and harassment, inadequate implementation of occupational health and safety measures among others.  The project workforce is expected to include direct workers only: CIZ staff, and a small number of consultants engaged directly by the CIZ (i.e. Consultancy on strengthening the enabling environment for improved, gender-balanced WASH at schools). Where government civil servants (i.e. Ministry of Public Service, Labour and Social Welfare, Ministry of Primary and Secondary Education, Ministry of Environment, Water and Climate and Ministry of Finance) are involved with the project, this will be only in an oversight and coordination capacity rather than any direct implementation. Whether full-time or part-time, they will remain subject to the terms and conditions of their existing public sector employment agreement or arrangement.

Mitigation Measures:

- Implement Labor Management Procedure (LMP) (See Annex 1) which includes  appropriate terms and conditions of employment, restrictions on child and forced labor, and occupational health and safety (OSH), drawing on national laws and regulations and international best practices.

- All consultants engaged by the project shall receive training on OHS and GBV/SEA/SH risks and be required to sign a CIZ code of conduct.

- Provide a Grievance Redress Mechanism (GRM) for all direct workers and contracted workers (consultant) to raise workplace concerns.  The grievance mechanism (GM)  receives, registers and addresses concerns and grievances related to the GBV/SEA-H in a safe and confidential manner, and  includes the referral of survivors to GBV/SEA-H service providers.

- Individuals under the age of 18 will be prohibited from working on the Project using national laws and regulations. The use of forced labor or conscripted labor on the project is also prohibited. All workers shall be required to have National Identification to verify their age.

### Gender Based Violence

Gender-based violence and/or sexual exploitation, abuse and harassment (GBV/SEA-H), is a potential impact that may occur during implementation of the project.  The pilot will provide monthly unconditional cash transfers to households with adolescent girls who currently benefit from the BEAM school fee waiver program. The project notes on a preference for female household representatives as both household representative recipients for both the household grants and the IGA grants. In a patriarchal context, men often control household resources, while women have limited agency in access, control and use of productive resources. Given this context, risks of intimate partner violence are pertinent especially over control and of the monthly cash transfers. There is a potential of GBV conflicts over prioritization and procurement for household consumption. There could also be potential for sexual exploitation and abuse of power over programme enrolment on potential beneficiaries. There is also the risk of GBV/SEA/SH from community members or project workers during both the household and school-level interventions, due to the contextual risks of GBV in Zimbabwe.

Mitigation Measures

- Adopt and implement a GBV/SEA-H Action Plan (Annex 3); sensitisation, awareness and training strategies with clear referral pathways in collaboration with communities and local women groups and women rights organizations

- Establish Codes of Conduct (including SEA-H), drawing on national laws and regulations and international best practices

- Ensure that the codes of conduct and GBV/SEA-H prevention provisions are integrated into all contractual and contracting documents (ToRs, tender documents, and workers’ contracts ); and (iii) ensure all staff are trained on SEA-H risks and sign the codes of conduct before starting work on any project activities.

- Capacity-building activities, under component 2 of the project,  will explicitly address gender inequalities and GBV in program participation. The capacity-building activities will focus on gender dynamics in sexual and reproductive health (SRH), root cause analysis of GBV within households, as well as gender-responsive education.

- Adopt and raise awareness on a  Grievance Mechanism for the community which is accessible and GBV sensitive.

### 6.2.10	Exclusion of Vulnerable Groups

There is the potential of exclusion of vulnerable groups, and other rural and marginalized groups who will not be eligible or will not be selected for this pilot (for example, persons with disabilities, extremely poor households and  adolescent girls). Exclusion could also be due to individual’s availability challenges limiting participation of selected adolescents. Various reasons can include being constrained by access to transportation to project venues and competing responsibilities and lack of time. They may also be constrained by lack of support from their household or other groups who hold influence and power, especially over adolescent girls.

Mitigation Measures:

- Project to initiate application of  differential approaches to ensure participation of vulnerable groups or those with special sensitivities (i.e religious/ traditional values) and that project design does not disproportionately exclude such groups.

- Implement the SEP and ensure regular dissemination of information on project status, using appropriate means such as sensitive local language to cater for different groups and promote inclusivity of all beneficiary stakeholders.

- Organise for small and focused meetings to help vulnerable groups feel more comfortable

- The eligibility criteria for selection beneficiaries shall be explained to the all stakeholders during the stakeholder consultation throughout the project period.

### 6.2.11 Transparency in Project Benefit Delivery

The lack of transparency and accountability in selection of pilot project beneficiaries could lead to lack of trust in BEAM community selection committee and administration as well as conflicts over unclear exclusion criteria. If risk control measures are not transparent, there is a likelihood of fraud from project field staff were sexual harassment, exploitation and abuse of power of power can lead to exploitation and abuse of female community members to influence enrolment into the cash transfer intervention.

Mitigation Measures:

- Use the Stakeholder Engagement plan to ensure all stakeholders are involved and communities are sensitized about the project, the selection process, and its objectives.

- Adopt the GBV, SEA-H action plan (Annex 3)

- Adopt the GRM that is accessible to community members (see Section 7).

## 6.3	Environmental and Social Management Plan

The E&S risks are moderate. The project will be implemented in accordance with the Environmental and Social Management Plan (ESMP)( Table 2) and will apply the relevant requirements of the Environmental Health and Safety Guidelines (EHSGs) to achieve safe water for menstrual hygiene outcomes. Different stakeholders including project managers, school health staff, village workers have different responsibilities in ensuring the implementation  as well as monitoring of the ESMP as described in Table 3.

Table 2: Environmental and Social Management Plan

| Project activities | IMPACT TYPE | POTENTIAL IMPACT | MITIGATION MEASURES | Responsibility | Monitoring indicators |  |  | Cost (USD$) |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Component 1: Household-level Interventions- Cash transfer, Income Generating Activities (IGA), hygiene promotion and menstrual hygiene products |  |  |  |  |
| Provision of Menstrual hygiene kits | Solid Waste – menstrual waste | Environmental pollution | - Provide bio-degradable unscented/ undeodorized pads or menstrual cups to adolescent girls. - Educate and provide proper guidelines on disposal of sanitary pads including dumping in latrine pits or deep burial only for bio-degradable menstrual hygiene waste ( see Annex 2) - Educate on dangers of dumping of disposable sanitary ware with plastic inlays or in polythene bags in pit latrines or mixing with household waste. - Educate on site disposal including deep burial, (of compostable/bio-degradable pads only ) especially in schools - Consider providing re-usable pads, period pants, menstrual cups - Place sanitary disposal bins in school toilets in places that do not compromise the privacy and dignity of the adolescent girls. | School Health Staff, Village Health Workers | Communities/ Adolescent girls Sensitisations conducted Physical inspections done |  | 10usd per set totalling 102 000 for 850 girls for the project life cycle |  |  |  |  |
| Provision of menstrual hygiene kits | Air Quality | Emissions from pit burning of sanitary waste | - With use of compostable menstrual hygiene kits, these can be disposed in pit latrines. - Training on Safe disposal of menstrual waste and guidance from the local EHT on location and maintenance of the disposal pits | School Health Staff Village Health Workers, EHT Officers | Pit locations cited |  |  |  |  |  |  |
| Provision of menstrual hygiene kits | Impact on soils | Contaminated soils | - Provide unscented/ undeodorized bio-degradable sanitary ware to adolescent girls. - Educate on proper disposal of biodegradable sanitary pads without polythene bags both at home and in schools - Use WHO guidelines on deep burying or pit burning only for pads made with natural fibres | Village Health Workers, School Health staff; EHT Officers | Communities/ adolescents trained Pits located using EHTs guidance |  |  |  |  |  |  |
| Water resources and water quality | Using water for menstrual hygiene contaminated with bacteria and pathogen | Contaminated water resources | - Promote use of safe water sources such protected wells and boreholes. - Provide chlorine tablets for water purification following supplier guidelines ( see Annex 5). - Provide training and guidelines on proper disposal of menstrual hygiene waste | Village Health Workers MoHCC officials ( EHTs) | Communities and adolescents trained Provision/ distribution of water tablets | USD71,400 at unit cost of USD340 for a box (with 10000packs with a strip of 30 each) |  |  |  |  |  |
| Provision of menstrual hygiene kits Strengthen water -related hygiene behaviours | Community Health and Safety | Community exposure and escalation in conflicts | - Implementation of the Stakeholder Engagement Plan (SEP) is the primary mitigation measure for addressing the risk of misinformation through sharing information and undertaking meaningful consultation regarding the pilot project. - Information about the pilot will be disclosed through social media, and the local media, FBOs - Beneficiaries and the public can also access information, raise questions, and file grievances through community level established community grievance mechanisms (CGM) channels. - COVID-19 safety protocol has been developed as part of the ESMP in annex 4 and shall be implemented throughout the project. - Guidelines on use of water purification tablets and guidelines for the appropriate disposal of menstrual waste materials. - Meetings to be held during the day at accessible points | Project Implementation Entity | SEP developed ESMP Developed |  |  |  |  |  |  |
| All activities | Labor | Forced labour/child labour | - Implement Labor Management Procedure (LMP) to include appropriate terms and conditions of employment, non-discrimination, and equal opportunity (which includes a safe work environment free from violence and sexual harassment), workers’ organizations, restrictions on child and forced labor, and occupational health and safety (OSH), drawing on national laws and regulations and international best practices. - All consultants engaged by the project shall receive training on OHS and GBV/SEA-H risks and be required to sign a code of conduct - Provide a Grievance Redress Mechanism (GRM) for all direct workers and contracted workers to raise workplace concerns. The grievance mechanism (GM) shall also receive, register and address concerns and grievances related to the GBV/SEA-H in a safe and confidential manner, and shall include the referral of survivors to GBV/SEA-H service providers. - LMP to establish Codes of Conduct (including SEA-H), and GM for worker grievances, drawing on national laws and regulations and international best practices. - Individuals under the age of 18 will be prohibited from working on the Project by national laws and regulations | CIZ Programme Management Human Resources | LMP Developed |  |  |  |  |  |  |
| Provision of menstrual hygiene kits | Occupational Health and Safety | COVID-19 exposure ; GBV and SEA-H | - All project staff and communities trained on COVID-19 prevention protocols.. - SEP adopted as the primary mitigation measure for addressing the risk of misinformation through sharing information and undertaking meaningful consultation regarding the pilot project. - GBV/SEA-H Action plan adopted - Ensure that the codes of conduct and GBV/SEA-H prevention provisions are integrated into all contractual and contracting documents (ToRs, tender documents, and workers’ contracts ); and (iii) ensure all staff are trained on SEA-H risks and sign the codes of conduct before starting work on any project activities - Establish Codes of Conduct (including SEA-H), and GM for worker grievances, drawing on national laws and regulations and international best practices - Workers to sign the codes of conduct before starting work on any project activities | Programme Managers | PPE for project officers procured Adoption of GBV action plan Adoption of SEP activities |  |  |  |  |  |  |
| Cash transfer Income generating and capacity building | Gender Based Violence; Security threats | Intimate Partner Violence, Sexual harassment and exploitation; Thefts | - Prepare, adopt, and implement a GBV/SEA-H Action Plan; - Beneficiaries to change mobile money withdrawal centre monthly to mitigate thefts. | Programme Managers | GBV/SEA-H Action Plan GBV trainings conducted Mapping and Linkages with GBV service providers Signed code of conduct |  |  |  |  |  |  |
| Component 2: School-level Interventions- Sensitization, Capacity Building and WASH Promotion |  |  |  |  |  |  |  |  |  |  |  |
| Sensitisation and capacity building | Exclusion of vulnerable groups | Exclusion of vulnerable groups | - Implement SEP which will ensure inclusivity of all categories of beneficiaries | Programme Manager | SEP communication strategy in place |  | USD3525 |  |  |  |  |
| Sensitisation and capacity building | Occupational Health and Safety | COVID-19 exposure | - Provision of adequate and required personal protective equipment (PPE) to project officers and ensuring all project participants adhere to COVID-19 prevention protocols | Programme Manager |  |  |  |  |  |  |  |
| TOTAL BUDGET |  |  |  |  |  |  |  |  |  |  |  |

## ESMP Monitoring

The table below outlines the monitoring of the ESMP implementation plan. It follows the impacts and mitigations identified in Table 2 above and provides the performance indicators, monitoring requirements, frequency as well as responsibility for monitoring.

Table 3: ESMP Implementation plan monitoring

| Impact | Performance Indicators | Monitoring Requirements | Frequency | Responsibility |
| --- | --- | --- | --- | --- |
| Solid waste | - Provision of bio-degradable sanitary pads /menstrual cups - Trainings on menstrual waste management - Change in knowledge and practice on menstrual waste management. | - Physical and routine inspections to determine waste management mechanisms. | Monthly | Village Health Workers, School health staff |
| Air pollution | - Records of trainings on menstrual waste management | - Physical inspections | Monthly | School health staff; Village Health workers, Environmental Health Inspectors |
| Soils and water bodies | - Records of trainings on menstrual waste management | - Physical inspections | Monthly | Village Health Workers |
| Occupational Health and Safety | - Availability of COVID PPE for workers - Number of COVID cases recorded - SEA-H policy and code of conducts | - Documentation of GBV, SEA-H training given to workers - Observations on COVID protocols adherence | Training frequency conducted monthly or as needed | Project Management |
| Community Health and Safety | - Visual inspection, waste disposal - Cases of COVID recorded - Water purification trainings and guidelines | - Physical inspections | Monthly | Project Management |
| Gender Based Violence | - GBV Trainings - GBV/ SEA-H code of conduct - Links established with referral pathways | - Review of cases recorded and resolved | Monthly | Project Management |
| Exclusion of vulnerable groups | - Implementation of SEP | - Records of meetings | Monthly | Project Management |
| Child Labour | - National IDs checked at recruitment | - Inspection of documentation | Once off | Project Management |

## 6.4.1	Project Implementation Unit

The Project Management Unit is comprised of the Team leader, Assistant Project Manager, Cash  Officer supported by other technical specialists in the project who will be supporting on different level of effort (LoE) including an Education Specialist, Monitoring and Evaluation Specialist and Assistant, Economic Empowerment Specialist; Environmental Safeguards Focal Point (on LoE); Social safeguard focal point (on LoE), Women Economic Empowerment Specialist ( on Loe) ;Gender Specialist ( on LoE); Project Field Assistant; Project Secretary; Driver and  Grants and Contracts Accountant(on LoE).

## 6.4.2	Organisational Structure/Organogram

Figure 3: CIZ Project Organogram

### 6.4.3	Zimbabwe Environment Management Authority

The Environment Management Authority (EMA) is responsible for ensuring environmental compliance in Zimbabwe and its staff will further ensure that the ESMP is implemented as part of their mandate, functions, and responsibilities.  EMA will undertake surveillance on the project implementation providing guidance on menstrual hygiene waste management and review compliance performance.

7.0 STAKEHOLDER ENGAGEMENT AND GRIEVANCE REDRESS

A detailed Stakeholder Engagement Plan (SEP) has been prepared by CIZ to identify the key stakeholders of the “Piloting social protection and wash interventions to keep adolescent girls in school in Zimbabwe” project establishing stakeholder engagement measures, including public information disclosure and consultation, throughout the entire Project cycle. An SEP is essential for the implementation of the ESMP as it provides a better perception of the  project context and any possible concerns that various stakeholders might hold. It ensures the effectiveness of the mitigation measures developed under the ESMP. The project has already conducted a stakeholder identification and analysis exercise. The project identified two levels of stakeholders as national-level stakeholders and community-level stakeholders. At the national level, the key stakeholder will be MPSLSW, particularly the BEAM team, as they will provide oversight of the pilot. Community level stakeholders were identified as adolescent girls, adolescent boys, parents/guardians and household members of adolescent girls, BEAM school staff, BEAM community selection committees and local leadership. Out of these two levels of stakeholders there are three categories into which they can be identified as follows:

- Affected Parties – persons, groups and other entities within the Project Area of Influence (PAI) that are directly influenced (actually or potentially) by the project and/or have been identified as most susceptible to change associated with the project, and who need to be closely engaged in identifying impacts and their significance, as well as in decision-making on mitigation and management measures. These include adolescent girls, adolescent boys, BEAM school staff, BEAM community selection committee; local leadership and parents/guardians and household members of targeted adolescent girls.

- Other Interested Parties – individuals/groups/entities that may not experience direct impacts from the Project but who consider or perceive their interests as being affected by the project and/or who could affect the project and the process of its implementation in some way. These includes the District Development Coordinator, the Buhera Rural District Council, Ministry of Health and Child Care; MoWACDSME, the press and media houses, civil society organisations and the public.

- Vulnerable Groups – persons who may be disproportionately impacted or further disadvantaged by the project(s) as compared with any other groups due to their vulnerable status, and that may require special engagement efforts to ensure their equal representation in the consultation and decision-making process associated with the project. These will include adolescent girls, people with disabilities and extremely poor households in the targeted area.

The SEP outlines how, when, and ways in which the project team will communicate and consult with stakeholders including vulnerable groups and a mechanism by which people can raise concerns, provide feedback, or make complaints about the project and its related.

The project has been guided by the SEP in engaging, sensitisation and public information disclosure through different platforms of the various identified stakeholders including meetings with interested parties; community sensitisation meetings, institutional sensitisation meetings with schools, distribution of IEC including posters and flyers.

The SEP has been prepared according to Environmental and Social Standard 10 (ESS 10) on Stakeholder Engagement and Information Disclosure of the World Bank’s Environmental and Social Framework (ESF) and will cover the whole project life cycle.

## Objectives:

The overall objectives of an SEP as stated in the ESS-10 are to:

- Identify the roles and responsibility of all stakeholders and ensure their participation in all stages of the project cycle.

- Establish a systematic approach to stakeholder and citizen engagements that will help to identify stakeholders and build and maintain a constructive relationship with project-affected parties.

- Assess the level of stakeholder interest and support for the project and to enable stakeholders’ views to be considered in project design and environmental and social performance.

- Promote and provide means for effective and inclusive engagement with project- affected parties throughout the project cycle on issues that could potentially affect them.

- Ensure that appropriate project information on environmental and social risks and impacts is disclosed to stakeholders in a timely, understandable, accessible, and appropriate manner and format taking special consideration for the disadvantaged or vulnerable groups.

- Provide project-affected parties with accessible and inclusive means to raise issues and grievances and allow the Project Implementing Entity and its Project Management Unit to respond to and manage such grievances.

## 7.1	Grievance Mechanism

CARE has an existing grievance redress mechanism in place to receive concerns, complaints and grievances from community project participants, stakeholders, learners, and care staff members. The existing Grievance Mechanisms (GM) will be adapted to receive stakeholders’ complaints and grievances ensuring the system addresses any complaints or concerns and offers mediation within a reasonable time during the lifecycle of the pilot project.

The GM also ensures that during the project life cycle, measures are taken to inform and raise awareness amongst project participants about the feedback and complaint mechanisms, know how to submit a report, and can give feedback freely, without fear of retribution. All language, reading, visual, and psychosocial barriers will be accounted for and addressed.

### 7.1.1	Objectives

The GM is intended to:

- Provide avenues for stakeholders to seek information and provide suggestions/ feedback on the project.

- Provide project affected people with avenues for lodging concerns, complaints and resolving a dispute arising from project activities.

- Ensure that appropriate and mutually acceptable redress actions are identified and implemented to the satisfaction of complainants.

- Provide avenue for vulnerable groups and victims of SEA/SH to have equal access to grievance redress process and support.

The project will abide by national laws and grievance redress mechanisms, however, the project’s GM will serve as a primary point for redress for project affected persons to amicably seek amends to their complaints. Nonetheless, aggrieved persons would remain free to access the national legal system without any hindrance or retribution from the project.

### 7.1.2	Principles of the GM

The operationalization of this GM shall be guided by the following principles.

- An accessible, inclusive, and free grievance mechanism (GM), broadly disclosed, which facilitates the resolution of concerns and grievances in a safe, confidential, and timely manner.

- A grievance mechanism that allows stakeholders to file complaints by various means (face-to-face, mail, email, phone, text, website, and in person) and when necessary, in an anonymous manner.

- A grievance mechanism that provides a clear, impartial, and objective procedures for handling and responding to complaints, including timelines for acknowledgement, decisions, and appeals.

- A grievance process that is free of retaliation, abuse, or discrimination.

- A grievance mechanism that is survivor-centred and provides an avenue for lodging SEA/SH cases in a safe, confidential, and non-stigmatizing manner and with a referral pathway for such cases.

### 7.2	Internal Management of the GM

The overall management of the GM will reside with the designated Project Team Leader working together with the project management unit comprising of the Education Specialist, Women Economic Specialist, Gender Specialist, MEAL Specialist, who will form a Complaints Management Team. The Meal Specialist will collaborate with the Communication Specialist in receiving and managing complaint processing whilst the Communication Specialist manages the complaint resolution process.

This team will specifically be responsible for:

- The disclosure of the GM to project stakeholders.

- Sensitization of implementing partners and staff on the GM.

- Receiving and managing complaint processing including updating, and closing complaints.

- Checking if all grievances have been addressed and follow-up actions have been taken.

- Escalating cases and serious complaints to PMU

- Referring survivors of SEA/SH cases to Gender Based Violence (GBV) service providers

- Monitoring and producing biannual performance report on the GM.

## 7.4	Description of Grievance Mechanism

CARE has an existing grievance redress mechanism in place to receive concerns, complaints and grievances from community project participants, stakeholders, learners, and care staff members. The existing grievance mechanisms will be adapted to receive complaints and grievances during project implementation and will entail:

- Complaint’s uptake

Submission of grievances will either be orally or in writing to any member of the Complaints Management Team. To ensure the GRM is accessible to all stakeholders, particularly vulnerable groups within the community, specific measures will be explored during consultations and reflected in the updated SEP. The GRM will also allow anonymous grievances to be raised and addressed. Internal staff will raise grievances in writing and submit it to one’s immediate supervisor. CIZ always ensures that, project participants have at least two channels for giving feedback, depending on what communication options exist in a given location.  Options will include:

- Information stations/Desks staffed by both women and men, with separate areas for women and men at the distribution or community meeting sites.

- Suggestion/Feedback boxes at each distribution site.

- A Delloite tip of anonymous toll-free line for beneficiaries/participants and stakeholders. The information will be accessed by the Country Director for confidentiality and ensuring proper actioning. In addition, a WhatsApp number will also be shared for feedback.

Use of the feedback mechanisms is clearly outlined through distribution of informational materials provided before and during distribution and through pre-distribution community meetings.

- Complaint’s sorting, processing and resolution:

The project will address all these complaints within a reasonable time (Investigating the grievance and Communication of the Response within 7 days), protect against retaliation and allow for escalation of complaints if not resolved in time by the project this should be reported to the Project Implementation Entity (PIE). Additionally, CIZ has a broad team with different job functions and roles for complaints processing:

- The Project Team leader together with the Project management unit (Education specialist, Women Economic Specialist, Gender Specialist, MEAL Specialist) are the overall Complaints management team responsible for overseeing project management and operations.

- The Meal Specialist collaborates with the communication specialist in receiving and managing complaint processing.

- The Communication Specialist: manages complaint resolution.

- Deputy director: manages operational leadership.

- The country director manages commitment and accountability.

All feedback will be collected by the MEAL and Communications Team and channeled to the CIZ Project Management Unit. The project will ensure that the MEAL and communications team is staffed by both women and men, to accommodate gender sensitivity needs. For extended cash distributions, information on feedback received and resolved will be provided to the CARE MEAL team through monthly reporting. Serious complaints (such as sexual abuse, child abuse, fraud, and/or corruption) are be shared immediately with CIZ project management unit. The project management unit led by the MEAL specialist monitors:

- Type of complaint, feedback, and/or question received.

- When it was received.

- Whether the complaint, feedback or question acknowledged.

- Status of the complaint (closed, in progress, etc.).

- Areas for improvement

Complaints are tagged by area(site), focal team, etc., for efficient routing and processing, and are then categorized according to:

- Outside of project scope.

- Ideas for future consideration.

- Request for information.

- Programmatic complaint- Urgent.

- SHEA / GBV harassed complaint – urgent

- Breach of code of conduct-immediately pulled out of the system and referred to the Deputy Director who resolves according to policies.

A summary of the grievances received is included in the monthly and quarterly monitoring reports. A summary of the status of handling of the grievances received is also included in the monthly and quarterly reports to CARE’s Project management unit and to the World Bank. Confidentiality will be paramount in the treatment of complaints. The Code of Conduct expected of staff contracted to work on the project will be disclosed to the public through the stakeholder engagement plan and during the project inception meetings.

If grievances are repeated, unresolved or submitted by several people, this should be escalated to CARE country office and the government of Zimbabwe. The GRM should be broadly communicated to all stakeholders. In addition, the Government of Zimbabwe has a separate Grievance Redress Mechanism (GRM) to deal exclusively with those that involve workers employed by the government public service commission. The project Communications and accountability officer will be responsible for managing the project GRM.

## GBV/SEA/SH cases

- Handling of GBV/SEA/SH Cases: CIZ is guided by the SHEA policy to undertake safeguarding risk assessments and identify areas of safeguarding and sexual harassment, exploitation, and abuse, and child abuse risks, and document steps that are being taken to remove or reduce these risks. CIZ incorporates safeguarding measures into the project implementation cycle through collaborative program design approaches which involve partners and program participants, at all stages to produce better design, monitoring and evaluation of safeguarding. CIZ also ensures that multiple reporting mechanisms (prioritizing community based) for reporting sexual harassment, exploitation and abuse, and child abuse are accessible and sensitive to the differing needs of anyone wishing to report, including vulnerable adults and children most at risk of sexual harassment, exploitation and abuse, and child abuse, the communities we work with, our partners, and CARE Employees and Related Personnel. CIZ will always raise community awareness on the expected behaviors of CARE Employees and Related Personnel and on how to make a report and ensure that anyone responsible for receiving reports understands how to carry out their duties and handle them in a safe and confidential manner. CIZ will always ensure transparency with survivors around any obligations or actions that may need to be taken as a result of their report, including referral to third parties. All actions will be informed by an assessment of risk to all those involved.

- Response and follow up to GBV/SEA/SH reports. CIZ will provide support and assistance to complainants and to anyone who has experienced sexual harassment, exploitation and abuse, or child abuse by CARE Employees and Related Personnel. This may include medical treatment, legal assistance, and psycho-social support. CIZ support and assistance is informed by a survivor-centered approach, feasibility, and an assessment of risks to all those involved in the GBV/SEA/SH cases that would have been identified. The identity of the survivor is protected and channels to report GBV/SEA/SH apart from community-based channels used to complement existing platforms. The GBV/SEA/SH issues are highly sensitive and confidential thus the MEAL specialist and the APM will respond to these cases being assisted buy the Team leader.

# ANNEX 1: LABOUR MANAGEMENT PROCEDURES

1.0 INTRODUCTION

The Piloting Social Protection and WASH Interventions to Keep Adolescent Girls in School in Zimbabwe (P177168) is being prepared under the World Bank’s Environmental and Social Framework (ESF). Under the Environmental and Social Standard 2 (ESS2) on Labour and Working Conditions, the project is required to develop Labour Management Procedures (LMP) to promote sound worker-management relationships and enhance the development benefits of a project by treating workers fairly and providing safe and healthy working conditions

The overall objective of this LMP is to promote sound worker management relationships and enhance the development benefits of a project by treating workers in the project fairly while also providing them with safe and healthy working conditions. Accordingly, the purpose of this LMP is to facilitate the planning and implementation of the project by identifying the main labour requirements and the associated risks and determining the resources necessary to address the project-related labour issues. The LMP sets out general guidance relevant to different forms of labour but also issues and concerns that relate to COVID-19 considerations. This document may be adjusted as the project advances and as new categories of employees become involved in the various activities.

1.1 OVERVIEW OF LABOUR USE ON THE PROJECT

ESS 2 categorizes project workers into: direct workers; contracted workers; community workers; and primary supply workers. The project workforce is expected to include direct workers only: CIZ staff, and a small number of consultants engaged directly by the World Bank. Where government civil servants (i.e. Ministry of Public Service, Labour and Social Welfare, Ministry of Primary and Secondary Education, Ministry of Environment, Water and Climate and Ministry of Finance) are involved with the project, this will be only in an oversight and coordination capacity rather than any direct implementation. Whether full-time or part-time, they will remain subject to the terms and conditions of their existing public sector employment agreement or arrangement. ESS2 will not apply to such government civil servants, except for the provisions of paragraphs 17 to 20 (Protecting the Work Force) and paragraphs 24 to 30 (Occupational Health and Safety), which fall under the provisions for workers' safety, as outlined in ESS 2.

- Direct Workers. The project will engage the following key categories of workers as “direct workers”:

  - Project Implementation Entity (PIE): A Project Implementation Entity will be set up and comprises of the Team Leader, Assistant Project Manager, Cash Transfer Officer, M&E Assistant, Project Field Assistant and Project Driver. Other Team members will include Environmental Safeguards focal point ( from WASH); Grants and Contracts Accountant; Social safeguards focal person (from Education); M&E Specialist;  Women Economic Empowerment Specialist and Gender Specialist. The Project Management Unit  will consist of the Country Director and Assistant Country Director. The PIE shall be responsible for the day-to-day implementation, administration, financial management, procurement, monitoring and evaluation of Project as further detailed in the Project Operations Manual.

- Primary supply workers: There will be no primary supplier engaged  in this project

- Community workers:  Community workers will not be employed in relation to this Project.

2.0 ASSESSMENT OF KEY POTENTIAL LABOR RISKS

Project Activities

This pilot will test the effect and viability of strengthening the government’s social protection programs, specifically the BEAM fee waiver, with layered social protection and WASH interventions that allow more comprehensive support addressing the needs of vulnerable adolescent girls. The pilot will target BEAM households that contain adolescent girls and will work with public secondary schools who benefit from BEAM. The activities will include the following:

- Cash transfer to selected BEAM recipient adolescent girls’ households

- Income Generating Activities (IGA) and capacity building

- Strengthen water-related hygiene behavior

- Provision of Menstrual Hygiene kits

- Sensitization and capacity building meetings

- Promoting WASH at public secondary schools

Key Labour Risks

The key risk for project workers is COVID-19 transmission. Project activities at the household and school level and stakeholder engagement activities may increase the risk of transmission of COVID-19. Other potential risks are those related to labour and working conditions, such as work-related discrimination, Gender-based violence and/or sexual exploitation, abuse, and harassment (GBV/SEA-H) and Occupational Health and Safety (OHS) risks. The PIE will assess and address these risks by developing recruitment guidelines, procedures and appropriate OHS measures and applying relevant provisions of the Labour Act, Public Service Act and CIZ HR manual. In addition, the PIE will train all workers engaged in project activities, on the guidelines and protocols on how to protect themselves and the communities from the spread of COVID-19. In accordance with ESS2 and Zimbabwean law, due to the hazardous work situation, children under the age of 18 will not be allowed to work on the project. The use of forced labor or conscripted labor on the project is also prohibited. No other labor risks are considered to be significant. However, if other labor risks arise during project implementation, CIZ will develop procedures to prevent further impacts.

3.0 BRIEF OVERVIEW OF LABOR LEGISLATION: TERMS AND CONDITIONS

Below is the overview of the key aspects of the Zimbabwe Labour Act (CAP 28:01) with regards to terms and conditions of work (ESS2, para 11).

Wages and deductions

Part IV Section 12(1) of the Labour Act notes that every person who is employed by or working for any other person and receiving or entitled to receive any remuneration in respect of such employment or work shall be deemed to be under a contract of employment with that other person, whether such contract is reduced to writing or not. It states that an employer shall, upon engagement of an employee, inform the employee in writing of a number of particulars including of the employee’s remuneration, its manner of calculation and the intervals at which it will be paid. It also speaks of particulars of any bonus or incentive production scheme and any  other benefits provided under the contract of employment. The Labour Act clearly states that equipment or clothing required to protect the health and safety of the employee shall not be computed as part of the remuneration of the employee.

Part IV Section 12A(7) relates to deductions and states that the aggregate amount of permissible deductions that may be made from the remuneration of any employee in any pay interval shall not exceed twenty-five per centum of the employee’s gross remuneration for that interval. However, upon termination of an employee’s service, an employer may deduct from the total remuneration due to the employee an amount equal to any balance which may be due to the employer.

Working hours

Normal working hours are not clearly defined by the Labour Act. However, every industry Collective Bargain Agreement provides for minimum hours of work with the model Collective Bargaining Agreement recommending a minimum of eight hours per day, subject to the nature of the work, and 40 hours per week. This could be up to a maximum of nine hours a day.

Working hours are however, set out using the CIZ HR regulations and agreed upon in the contract which states that the employer may request, but shall not require an employee to work overtime, and shall, whenever possible, give twenty-four hours’ notice to such employee of such request. Provided that employees needed to render emergency, work shall not decline to work overtime without reasonable excuse

Rest breaks

Section 14C (1) of the Labour Act states that every employee shall be entitled to not less than twenty-four continuous hours of rest each week, either on the same day of every week or on a day agreed by the employer and employee.

Leaves

Part IV Section 14, 14A, and B of the Labour Act relates to sick leave, special leave, and vacations. It states that unless more favourable conditions have been provided for in any employment contract or inany enactment, paid vacation leave shall accrue to an employee at the rate of one twelfth of his qualifying service in each year of employment, subject to a maximum accrual of ninety days’ paid vacation leave. Where an employee has no vacation leave accrued, he may be granted vacation leave without pay. An employee shall be granted leave of absence during every public holiday and shall be paid his current remuneration for that day if it occurs on a day on which he would otherwise have been required to work. It also allows an employee to consent to work on a public holiday and be paid not less than twice his current remuneration for that day, whether that day is one on which he would otherwise have been required to work or not.

Part IV Section 18 relates to Maternity leave and grants women maternity leave on production of a certificate signed by a registered medical practitioner or State Registered Nurse certifying that she is pregnant. A female employee may proceed on maternity leave not earlier than the forty-fifth day and not later than the twenty-first day prior to the expected date of delivery. Paid maternity leave shall be granted only once during any period of twenty-four months calculated from the day any previous maternity leave was granted.

Overtime work

The Labour Act Chapter 28:01 addresses the issue of overtime in section 14C where it makes it mandatory to pay an employee who works overtime during a public holiday at double his or her normal rate of pay. The Labour Act further makes it compulsory to have an employee to consent to work on a public holiday, therefore, it does not make it mandatory. However, this provision must be read together with Collective Bargaining Agreements of the governing National Employment Council where work on public holidays can be made mandatory and the only legal requirement is paying employees at double the rate for work on public holiday Standard CBA note that the minimum overtime rate is 150% of the normal salary/wage rate when employees are required to work beyond the normal working hours. When an employee works on a public holiday, then a premium of 200% of the normal salary/wage is normally paid.

Labour disputes

Part XII  of the Labour Act focuses of resolution of disputes and unfair labour practices It states that a labour officer to whom a dispute or unfair labour practice has been referred, or to whose attention it has come, shall attempt to settle a dispute through conciliation or, if agreed by the parties, by reference to arbitration . However, if the dispute or unfair labour practice is settled by conciliation, the labour officer shall record the settlement in writing. Any party to the dispute may, in the time and manner prescribed, apply to the Labour Court with provisions for either or both of the following remedies including

- an order directing the employer or other party concerned to cease the infringement or threatened infringement, as the case may be.

- an order for damages for any loss or prospective loss caused either directly or indirectly, as a result of the infringement or threatened infringement, as the case may be.

4.0 BRIEF OVERVIEW OF LABOR LEGISLATION: OCCUPATIONAL HEALTH AND SAFETY (OHS)

This section sets out the key aspects of the national labour legislation with regards to occupational health and safety, and how national legislation applies to the different categories of workers identified in Section.

Occupational safety and health in Zimbabwe is regulated generally by the Factories and Works Act (20 of 1948), the Labour Act (28:01), the National Social Security Authority (Accident Prevention and Workers Compensation Scheme) Notice No. 68 of 1990 . The Labour Act defines the fundamental rights of employees and regulates conditions of employment (including issues relating to occupational safety and health). The National Social Security Authority (Accident Prevention and Workers Compensation Scheme) Notice provides comprehensive regulations for the prevention of occupational injuries and diseases; and the compensation of employment-related injuries and diseases.

The Occupational Safety and Health Policy assigns occupational safety and health responsibilities to both employers and employees. It also recognises that workers have various safety and health rights, including the right to refuse to undertake unsafe work. The policy states every worker’s right to fair and safe labour practices and to know the occupational safety and health risks that he or she is or is likely to be exposed to and their effects. Every worker also has the right to be consulted in the development of mechanisms that mitigate identified occupational safety and health risks and has the right to refuse to undertake any work that has not been rendered safe.

The policy highlights the importance of safety and health awareness and recommends that every new worker and visitor should be given an induction on the prevailing OSH risks, the system in place to manage them and the expected response to them. Employers should ensure that OSH information, training and systems address diverse needs and have a responsibility to ensure the proper use by workers of occupational safety and health protection systems, including personal protective equipment and clothing.

Workers, on the other hand, are required to take reasonable care of the safety and health of themselves and others. They are expected to cooperate with employers in their efforts to comply with the OSH policy and OSH requirements. They are required to follow procedures in the performance of any task at work. Workers are also prohibited from refusing a reasonable request to assist in giving aid or preventing a risk to safety and health. Both employers and employees are warned that they should not disrupt a workplace by creating safety and health fears. The policy says every employer should have occupational health services which will ensure, in so far as is practicable, that no worker shall suffer diminished health, functional capacity or life expectancy because of his work activities.

National Social Security Authority (NSSA) or any other authorised authority is expected to employ inspectors of workplaces to regulate practices at workplaces.

5.0 RESPONSIBLE STAFF

This section identifies the functions and/or individuals within the project responsible for

o	engagement and management of project workers

o	occupational health and safety (OHS)

o	training of workers

o	addressing worker grievances

The Project Implementation Entity will be comprised of the Team leader, Assistant Project Manager, Cash  Officer supported by other technical specialists in the project who will be supporting on different level of effort (LoE) including an Education Specialist, Monitoring and Evaluation Specialist and Assistant, Economic Empowerment Specialist; Environmental Safeguards Focal Point (on LoE); Social safeguard focal point (on LoE), Women Economic Empowerment Specialist ( on Loe) ;Gender Specialist ( on LoE); Project Field Assistant; Project Secretary; Driver and  Grants and Contracts Accountant(on LoE).

The Project Management Unit will be responsible for overall oversight of the Project Implementation Entity which will carry out the day-to- day project activities. The PMU as well as Team Leader and Assistant Team Leader from the PIE wil be responsible for

- engagement and management of project workers

- engagement and management of contractors/subcontractors

- addressing the worker grievances

| ENGAGEMENT AND MANAGEMENT OF PROJECT WORKERS |  |  |  |  |
| --- | --- | --- | --- | --- |
| Responsible | R | Responsible for performing the task (i.e. the actual person doing the work to complete the task). |  |  |
| Accountable | A | Ultimately accountable for the task being done in a satisfactory manner. (i.e. Supervisor or Team Leader) |  |  |
| Consulted | C | Team members whose input is used to complete the task. Communication with these members will be 2-way in nature. |  |  |
| Informed | I | Team members who are informed as to the status of the task. Communication with these members will be 1-way in nature. |  |  |
| Responsible |  | Accountable | Consulted | Informed |  |
| Team leader |  | Team leader | Human Resources | Rest Of PMU |  |
| The Team Leader is responsible for the engagement and management of the project staff. |  | Team leader oversees satisfactory implementation. | Human resources will be consulted with regards to the Staffing need and plans of the project and assist in the engagement, placement and management of the project staff. | PMU informed on engagements and termination. |  |
| OCCUPATIONAL HEALTH AND SAFETY (OHS) |  |  |  |  |  |
| Responsible |  | Accountable | Consulted | Informed |  |
| Assistant Project Manager |  | Team leader | Human Resources | Rest Of PMU |  |
| The APM will be responsible for the implementation of all OHS related policies at field level to ensure project staff execute their duty in a safe work environment. |  | The team leader is responsible for the ensuring compliance to OHS policy by the team. | HR will be consulted with regards to OHS policy and any legal compliance required with regards to OHS and the effective execution of duty. | The PMU will be informed on the status of OHS under the projects. |  |
| TRAINING OF WORKERS |  |  |  |  |  |
| Responsible |  | Accountable | Consulted | Informed |  |
| Assistant Project Manager |  | Team leader | Human Resources | Rest Of PMU |  |
| The APM is responsible for training of staff on project level policy content. The APM will be responsible for recommending training to HR based on identified training needs for the Project team. |  | Ensuring members are skilled to execute the mandates of the project as per Donor requirements. | Human resources will be consulted on all training need for the project. |  |  |
| ADDRESSING WORKER GRIEVANCES |  |  |  |  |  |
| Responsible |  | Accountable | Consulted | Informed |  |
| Team leader |  | Human Resources | Human Resources | Rest Of PMU |  |
| The Team Leader is responsible for ensuring a harmonious industrial relation and ensuring that all grievances and handled with fairness and Justice. |  | Human Resources is responsible in ensuring that the Grievance policy is upheld within the project. | HR will provide support in facilitating and handling employee grievances for the project and ensuring that this is handled as per national and industry guidelines. |  |  |

6.0 POLICIES AND PROCEDURES

This section sets out information on OHS, reporting and monitoring and other general project policies.

The project will be guided by the national Labour Act and OHS guidelines as outlined above. CIZ`s operations fall under Welfare and Educational Institutions. This industry`s labour practices are guided and governed by Statutory Instrument 102 of 2014- Collective Bargaining Agreement: Welfare and Educational Institutions, 2014. Collective Bargaining Agreement made in accordance with the provisions of the Labour Act [Chapter 28:01] between the Welfare and Education Institutions Employers Association (the “employers association”) and the Zimbabwe Educational Scientific Social and Cultural Workers Union (the “trade union”) being parties to the National Employment Council for the Welfare Educational Institutions. Below is a synopsis of the key aspects of the Zimbabwe Welfare and Educational Institutions Collective Bargaining Agreement Statutory Instrument 102 of 2014 with regards to terms and conditions of work.

| ESS2 (para 11) | Statutory Instrument 102 of 2014 |
| --- | --- |
| Payment of wages and deductions | Grades and wages Section 7 (1) |
|  | Every employer shall place each employee in a grade listed in the First Schedule appropriate to his or her occupation and shall pay a wage to such employee of at least the amount prescribed in the Second Schedule for the employee’s grade including any other prescribed employment benefits and no employee shall accept benefits less than the amount of wages and benefits prescribed. |
|  | Payment of wages and deductions Section 17 (1) |
|  | Every employer shall pay all remuneration including wages, overtime, bonuses and allowances, weekly or monthly, within three days of due date: Provided that, when an employee’s services are terminated, payment of all remuneration due shall be made within twenty-four hours of the termination of services. |
| Working hours and Overtime | Hours of work Section 12 |
|  | The ordinary hours of work for all employees shall not exceed forty-five hours a week, provided that the ordinary hours of work shall not exceed nine hours per day. An employer may request, but shall not require an employee to work overtime, and shall, whenever possible, given twenty-four hours’ notice to such employee of such request. Provided that employees needed to render emergency, work shall not decline to work overtime without reasonable excuse. |
| Rest breaks. | Hours of work Section 12 (6) |
|  | No employer shall require or permit and employee to work for a continuous period of more than five hours without a break of at least thirty minutes: Provided that an employer shall also permit his or her employees to have a ten minute break every morning between the third and fourth hours of work. |
| Leaves | Vacation leave Section 22 |
|  | An employee shall accrue vacation leave of two and a half (2.5) calendar days for each completed month of continuous service. Any portion of a month shall be regarded as full month |
|  | Industrial Holidays Section 23 |
|  | Every employee shall be granted leave of absence on industrial holidays and shall be paid his or her current daily wage for every industrial holiday |
|  | Sick leave Section 24 |
|  | An employee shall be granted sick leave subject to the provision of a medical certificate granted by a registered medical practitioner The employer shall be responsible for medical expenses incurred by an employee who is injured, through no fault of his or her own, in the course of his or her duties, where such expenses are not met by any applicable workers compensation or medical aid scheme |
|  | Special leave Section 25 |
|  | Special leave on full pay not exceeding twelve days in a calendar year shall be granted by an employer to an employee. Special leave will be granted based on the grounds stipulated in SI 102 of 2014 |
|  | Maternity Leave 26 |
|  | Maternity will be granted for a period of ninety-eight days on full pay on production of a certificate signed by a registered medical practitioner or State registered nurse certifying that she is pregnant, a female employee may proceed to maternity leave not earlier than the forty-fifth day and not later than the twenty-first day prior to the expected date of delivery. |
| Labor disputes | Resolution of Disputes Section 31 |
|  | A designated agent of the council may require any employer for which the council is registered to grant him or her or her reasonable access to his or her employees for the purpose of advising and assisting them in relation to their rights of employment and support in the case if disciplinary hearings are concerned |

The project staff will also sign CIZ HR Policies including:

- Grievance Policy

Every employee in CARE has a right to express a grievance in relation to their employment without prejudice to their employment or fear of discrimination or victimisation and seek redress for the grievance.

- Funeral Policy

The primary objective of the policy is to contribute towards the provision of emotional and material support to the bereaved family consistent with the family’s cultural values as far as is possible. In the event of the death of a CARE Zimbabwe employee, either on duty or not, this Policy will apply. This policy also relates to what the CARE employee can expect in relation to death of a family member. For purposes of this policy, a family member is considered; a registered /legal dependent; spouse, biological parents and children.

- Sexual Harassment, Exploitation and Abuse Policy

CIZ recognizes the rights of all individuals against sexual harassment, exploitation and abuse. Accordingly, CARE will promote and respect the rights of staff and beneficiaries by creating an awareness of what constitutes sexual harassment, exploitation or abuse and providing mechanisms for reporting these where they occur whether at the workplace or between our staff and beneficiary community. Sexual exploitation and abuse is prohibited behaviour and CARE has a zero tolerance policy to sexual, harassment, exploitation and abuse.

- Political Activity Restriction Policy

CIZ is restricted from participating or intervening, directly or indirectly, in a political campaign on behalf of (or opposed to) any candidate for public office. CIZ is subject to numerous restrictions on the types of public policy and advocacy activities in which it participates. The political campaign activity deals with candidates for public office.

- Occupational Health and Safety Policy.

CARE assesses the work or environmental risks posed to employees’ health and safety before deployment. Staff will then be empowered with skills necessary to identify health and safety hazards and stop operations when work is unsafe.

- Workplace HIV/AIDS Policy

The objective of the Workplace Aids Policy is:

- To establish a framework for a consistent response to HIV and AIDS among CARE staff within the workplace; and

- To mitigate the impact of HIV and AIDS at the workplace

- The following principles will be observed:

- Non – discrimination

- Non – stigmatization

- Creation of a conducive work environment and

- Equity and justice in the provision of services

- Gender Policy

This Gender Policy is a demonstration of CARE International in Zimbabwe’s high-level commitment to gender equality and women’s empowerment in its work and operations committing to gender transformative work at the organizational, programmatic and operational levels.

- CARE Zimbabwe Code of Conduct

# In varying measure, each employee represents the organization in his or her relations with others, whether clients, suppliers, other employees, governments, or the general public.  The organization expects each employee to act in a manner that will enhance CARE Zimbabwe’s reputation for honesty, integrity and the faithful performance of its undertakings and obligations.

7.0 AGE OF EMPLOYMENT

The Labour Act (Chapter 28:1) PART IV Section 11  states that no employer shall cause any person under the age of eighteen years to perform any work which is likely to jeopardize that person’s health, safety or morals, which work shall include but not be limited to work involving such activities as may be prescribed Documentary proof of age will be required prior to employment. Employment of young persons shall be in accordance with the provisions of the Labour Act and the Human Resources Department will ensure compliance with this provision. The Project will conduct an age verification exercise through the documentation of National IDs for the staff employed by the project to ensure compliance.

8.0 TERMS AND CONDITIONS

Specific wages, hours and other provisions that apply to the project are as follows:

Wages will be paid based on the CIZ remuneration policy. Employees are expected to arrive at work promptly in order to be at their workstation at start of CARE working hours. It is the duty of all employees to report to work on time every official working day. All CARE employees are expected to work a minimum of forty hours and a maximum of forty-five a week excluding scheduled holidays as follows: Monday – Thursday: 0800hrs - 1300hrs and 1330hrs – 17:15hrs  and Friday 0800hrs - 1300hrs

All employees shall be entitled to a thirty-minute lunch break from Monday to Thursday. Employees may be required to work outside the ordinary working hours.

9.0 GRIEVANCE MECHANISM

Every employee in  CIZ has a right to express a grievance in relation to their employment without prejudice to their employment or fear of discrimination or victimisation and seek redress for the grievance. When an employee feels aggrieved s/he shall follow the procedures laid out in the grievance policy.

Step 1: The aggrieved employee (the grievant) shall put in writing his grievance on a Grievance Form (available from HR) and submit it to his immediate supervisor.

Step 2: The immediate supervisor must take prompt action to redress the grievance. He/she will discuss with the employee to find out the cause of the grievance and find a solution to the grievance. The immediate supervisor will document the proceedings including his/her suggested solution to the grievance.

Step 3: If the employee is satisfied with the suggested solution, then there shall be no further recourse in connection with the grievance.

Step 4: If the employee is not happy with the suggested solution or the immediate supervisor is unable to solve the problem the grievant can take it up to their direct supervisor’s manager.

Step 5: If the employee is unhappy with the manager’s suggested solution, then the grievance will be submitted to Human Resources for resolution

Step 6: If the grievant is still unhappy with the resolution proffered by Human Resources the grievance will be submitted to the Country Director. When the Country Director has addressed the employee’s grievance there shall be no further internal recourse in connection with the grievance.

The Project workers’ grievance mechanism will not prevent workers to use conciliation procedure provided in the Labor Act.

10.0 CONTRACTOR MANAGEMENT

The project will not engage any contractors directly.

11.0 COMMUNITY WORKERS

The project will not engage community workers.

12.0 PRIMARY SUPPLY WORKERS

The project will not engage primary suppliers.

# ANNEX 2:  MENSTRUAL WASTE DISPOSAL GUIDELINES

Given the limited viable disposal options available in rural settings including logistical challenges in transporting waste to local district hospitals with incinerators, the main option for on-site safe disposal is the pit latrines for compostable menstrual hygiene waste.

Menstrual Hygiene management “safe disposal” means ensuring that where  there is menstrual hygiene management, the process of destruction of the used and soiled menstrual hygiene waste is done with minimal environmental pollution. Given the water constraints in the pilot area, use of reusable menstrual hygiene products is constrained, hence opting for disposable compostable/ bio-degradable menstrual hygiene management  products. These, as aforementioned, can be disposed in the pit latrines.  Though compostable menstrual hygiene management products can be thrown in pit latrines, there is another available option for on-site disposal, deep burial which should be a  pit with  minimum dimensions of 1m(L)x1m (W)x1m (D). This should be far from water sources ( at least 5 metres horizontal distance and 2m vertical distance) and 5-7m from homesteads.  Following the WBG General EHS Guidelines public access to the pit should be prohibited, ensuring safe delivery of the waste to the pit site. The pit should only be half filled with waste and can include kitchen compostable waste before covering with soil or sand immediately after disposal

# ANNEX 3: Gender Based Violence Action Plan

| Activity to Address GBV/SEA/SH/VAC risk | Steps to be taken | TimeLines | Responsible | Who will monitor | Output Indicators | Budgets (USD) |
| --- | --- | --- | --- | --- | --- | --- |
| Designate a GBV/SEA focal point to supervise and provide technical support for the implementation of GBV and SEA-H Action Plan | Develop ToR for Gender focal person | Immediate | Assistant Project Manager | Assistant Project Manager | Project Reports | Level of Effort from Start for Girls |
| Support capacity of local systems to prevent and respond to GBV, SEA-H (Village committees; CBO’s). Strengthen the reporting mechanisms & procedures of local systems. | Identify key stakeholders to engage Develop training plan Develop training material/ content Develop coordination and reporting mechanism | Continuous | Gender Focal Point | Assistant Project Manager | List of trained stakeholders Number of trainings conducted | 5000 |
| Strengthen a survivor centered referral and response. Strengthen coordination for better services with local GBV, SEA-H service providers | Incorporate survivor centered approaches Conduct training and mentoring Conduct regular coordination meetings with service providers for effective referrals | Continuous | Gender Focal Person | Assistant Project Manager | Number of coordination meetings conducted Readily available materials for reference | 9000 |
| Conduct GBV training for project staff/team to include: - HR policies on SEA/SH - Code of Conduct on GBV, SEA-H - SEA-HH reporting and allegation procedures | Develop a training plan Develop training materials Conduct training for project staff | Immediate | Gender focal person and ESM Focal person | Team Leader | GBV trainings conducted for project staff Activity Reports | 1300 |
| Develop M&E programme | Develop an M&E plan to monitor work plan implementation Monitor GBV, SEA-SH Implementation Plan | Immediate | Monitoring Specialist/ Gender Focal Person | MEAL Specialist | M&E framework in place Number of monitoring activities done and reports produced on quarterly basis | LOE 500 |
| Develop information dissemination strategy for GBV, SEA-H | Develop a strategy Identity the methods to disseminate the information Dissemination of information publicly to stakeholders | Immediate | Gender Focal Person | Assistant Project Manager | A SEA/SH communication strategy in place No of IEC materials disseminated | 4000 |
| Develop/adapt relevant IEC materials for community engagements | Develop relevant IEC materials translated in local language | Immediate | Gender Focal Person | Assistant Project Manager | Number and type of GBV; SEA-H IEC material developed | 4000 |
| Conduct community sensitization and capacity building on GBV; SE- H risks, sexual and reproductive health (SRH), positive parenting and saving to support the girl child | Develop a community sensitization and capacity building plan, material and messages. | Immediate | Gender Focal Person | Assistant Project Manager | Number of community sensitizations conducted Report of the activity with clear action points | 5800 |
| Establish partnerships with key stakeholders (CSO’s) on prevention and response of GBV | Identify and select partners Engage partners, conducting joint Community meetings and awareness raising | Immediate | Gender focal person | Assistant Project Manager | Partnership map/report | 5800 |
| Incorporate GBV//SEA-H Requirements and expectations in the contractor/suppliers/consultants’ contracts | Ensure that SEA/SH issues are incorporated in all contracts signed by contractors/consultants/ suppliers | Immediate | Human Resources | Team Leader | SEA/SH standards in procurement contract document | LOE |
| Codes of Conduct (CoC) signed and understood | Define the requirements to be included in the CoC which addresses SEA/SH Review CoC for provisions/clauses that guard against SEA/SH Have CoCs signed by all contractors /suppliers / consultants. | Immediate | Human Resources | Team Leader | Contract documents with clearly defined SEA/SH clauses /requirements Signed CoCs | LOE |
| Develop/Review GRM for specific SEA-H procedures | Undertake internal review of GRM for SEA/SH mitigation Integrate SEA/SH entry points within the GRM with clear procedures Update SEA/SH reporting and allegation procedures. | Immediate | Gender Focal Person | Team Leader | GBV/SH procedure integrated CIZ- GRM module | LOE |
| Identify and train community SEA-H focal points within the GRM who shall be responsible for handling SEA-H cases and make referrals to relevant stakeholders. | Identify and select GBV-SEA focal persons within the GRM Clarify the role of the focal points in GBV/SEA as referral points Train the focal points on GBV/SEA basics and the referral pathway | Immediate | Gender Focal Person | Assistant Project Manager | Number of focal persons identified and trained in all districts Number of GBV cases received, referred, and resolved | 4800 |
| Review GRM reports/logs for GBV/SEA sensitivity | Review logs for GBV/SEA documentation to ensure it follows standards for documenting GBV/SEA cases. | First and second months | Gender Focal Person | Team Leader | Number of reviews done on GRM reports | LOE |
| BUDGET TOTAL |  |  |  |  |  | USD40,200 |

# ANNEX 4: CIZ COVID PROTOCOLS

# ANNEX 5: STAKEHOLDER ENGAGEMENT PLAN

# ANNEX 6: Aquatabs for Water purification

Product description

Oasis® Water Purification Tablets are effervescent chlorine tablets with Sodium Dichloroisocyanurate (NaDCC) also known as Troclosene Sodium as the active ingredient. The tablets are available in foil-wrapped strips of different strengths, according to the volume of water to be treated, from 1 to 200 L.

Product Illustrations

- Available as: PACK/BOX SIZE: Packs of the above

- BOX SIZE: Box of 3200 strips of 10 Tablets (See images for box of 3200 strips)

- Quickly makes your water safe to drink in 30minutes.

- Substantially reduces contamination in filtered water chlorine-based tablets. Neutralises bacteria and helps to protect you against water transmitted ailments.

### Instructions for use

- 1 x tablet treats 1 litre

- Instructions notes illustrated at the back of the strip.

### Action of Chlorine tablets

The chlorine dissolve quickly in water, for best result let them work for 30 minutes. The microbial killing action is due to its capacity to destroy the bacterial cell wall on exposure. Its activity spectrum works against hydrophilic viruses, bacteria, fungi, and protozoans.

### Is chlorinated water safe for consumption:

Chlorine may be harsh against the disease-causing bacteria but it gets neutralized in our body. Also, the concentration of chlorine in chlorine is sufficient to kill the pathogens bit is probably too low to cause any significant injury in humans.

### When to use:

- Purification of drinking water.

- Disinfection of fruits and vegetables.

### Benefits:

### Chlorine gets converted to chloramines that produce no harmful residues.

- Effective against all virtually known pathogens

- Easy to store and transport

- Great biocidal effect

- Safe to handle

- Environment friendly

- Quick action

- Inexpensive disinfecting agent

- Economical disinfecting agent

- Easy to use

- Biocidal agent

- Can be stored for a long time

- Portable

- Effective against a wide range of pathogens

- No harmful residues

The tablets are available in accurate doses yet people with allergy to chlorine and pregnant women should avoid them.

### Dosage

Tablets usually come in different sizes in correspondence to the amount of water that needs to be disinfected. Generally, 1 mg of the tablet is sufficient for 1 litre of water. Chlorination of water is a concept of water purification that has been irreplaceable over the years. The chlorine tablets are inexpensive, easy to use, with quick action, and ensure potable water.

### Variety

These chlorine tablets are available in portable forms such as strips or even small liquid containers(water guard). These alternatives give users ease to use for domestic drinking water.

### Application

- Safe drinking water: Chlorine provides potable drinking water because of its disinfecting and sterilizing properties. The addition of chlorine to drinking water as restricted the frequent episodes of water-borne diseases to a great extent.

- Household disinfectant: Chlorine being a bleaching agent, can not only disinfect clothes but also whitens them. Chlorine and water solution can be used for household cleaning purposes, especially the surfaces that are prone to contamination.

- Disinfecting eatables: As diluted chlorine is safe for human consumption it can be used for washing fruits and vegetables. Thus, chlorine has the capacity to fight food borne pathogens as well.

https://www.efchlor.com/product/chlorine-tablets/

# ANNEX 7: Aquatabs Material Safety Data Sheet

# ANNEX 8: TERMS OF REFERENCE

Environmental Social Management Plan for the Social Protection and WASH Pilot project to keep adolescent girls in school.

# 1. Background

Social Protection and WASH interventions to keep adolescent girls in school Pilot Project Profile

The World Bank is funding a pilot in Zimbabwe that by layering Social Protection and WASH interventions targeting adolescent girls who have been disproportionately affected by coping mechanisms adopted during lockdown, aims to support their return to school after several waves of school closure in Zimbabwe. This pilot aims to inform the future policies and programming of the Ministry of Public Service, Labor and Social Welfare (MPSLSW) and other relevant ministries and strengthen their capacities. The pilot will be directly layered over Government’s Basic Education Assistance Module (BEAM) fee waiver program to test whether complementary social protection and WASH interventions are successful in bringing adolescent girls back to school and incentivizing them to stay in school. It will therefore test the effectiveness of complementary measures to the national BEAM program, beyond the fee waiver for vulnerable children, by focusing on gender dimensions and targeting vulnerable adolescent girls within the BEAM caseload. Specifically, the pilot will provide household and school level social protection and WASH support that aim to mitigate negative coping mechanisms that affect adolescent girls, improve access to WASH and menstrual hygiene management, and sensitize households and schools on gender dynamics, GBV, amongst others. The pilot will be implemented by CARE International Zimbabwe (CIZ) in collaboration with MPSLSW and relevant ministries.  Knowledge generation and policy dialogue will be undertaken on the findings and recommendations from the pilot towards strengthening government capacity. The pilot will be implemented in Buhera district and a process evaluation will be carried out by a third party. The pilot is comprised of two components:

Component one (1) of the pilot focuses on household-level interventions. These include a multi-purpose monthly cash transfer of US$ 35 per household for a six-month period to help meet basic food and non-food needs of beneficiary adolescent girls and are intended to discourage households from employing negative coping strategies that impact adolescent girls. Households will also receive a Income Generating Activity (IGA) grant of US$ 250 to fund business plans developed with the support of the pilot through the Start4Girls project. These will be complemented with targeted capacity-building and training focused on business skills, financial literacy, etc.  Adolescent girls will also receive 12 menstrual hygiene kits to last them one year, which will include sanitary pads, soap and underwear. In addition, households will receive support to improve water-related hygiene behavior that will help promote hygiene and will also provide chlorine tablets for water treatment.

Component two (2) of the pilot focuses on school-level interventions. This component will work closely with public secondary schools with children receiving BEAM support the promotion of positive gender norms, sexual and reproductive health messaging, good hygiene and menstrual hygiene management including raising awareness among adolescent girls. The pilot will organize sensitization and capacity building meetings covering two main areas. The first will be biweekly sensitization and capacity building meetings held in schools at a date and time chosen collectively by students targeting boys and girls at school, as well as their parents, where appropriate. These sessions will aim to mitigate negative coping strategies, adopted in times of domestic economic hardships where households forgo nutritional, hygiene and other needs resulting in prioritization conflicts amongst household members. Sessions wil focus on gender dynamics will touch upon sexual and reproductive health (SRH), gender-based violence (GBV), and menstrual hygiene management, among others. There second set of meeting will be bi-monthly meetings for school staff focusing on WASH. Sessions for school staff will focus on gender responsive education and girl friendly WASH and menstrual hygiene management.

The project is in its stages and the following input is sought from stakeholders, particularly government partners and the community:

•	A multi-stakeholder and participatory approach will be adopted to enable finetuning of the selection criteria for households. Input from MPSLSW, schools and the community will be vital to finalizing the selection criteria and process for the project. The project will target households with adolescent girls who are part of the BEAM program, but further selection criteria will need to be identified to obtain a final group of participating households.

•	Household-based WASH support. Component 1 of the project includes the provision of support for WASH management to the participating households based on identified needs and gaps.

•	Timing and content of the project Sensitization, hygiene promotion and Capacity Building Meetings. Once participating households and schools have been identified, the project will work closely with them to identify appropriate times and locations for the Sensitization and Capacity Building Meetings. They will also be engaged to contextualize the content of these meetings to ensure that they are useful, acceptable and speak to the context of Buhera district.

# 2.Objectives of this Consultancy

The objectives of this consultancy are to develop an Environmental and Social Management Plan (ESMP) that details a set of mitigation, monitoring, and institutional measures to be taken during implementation and operation of a project to eliminate adverse environmental and social risks and impacts, offset them, or reduce them to acceptable levels. The ESMP shall also include the measures and actions needed to implement these measures.

# 3.Scope of works

The consultant is expected to undertake the following:

- Identify and summarize all anticipated adverse environmental and social impacts that may arise as a result of the project.

- Describe with technical details, each mitigation measure, including the type of impact to which it relates and the conditions under which it is required (e.g., continuously or in the event of contingencies), together with designs, equipment descriptions, and operating procedures, as appropriate.

- Identify monitoring objectives and specify the type of monitoring, with linkages to the impacts assessed in the environmental and social assessment and the mitigation measures described above.

- Provide guidance on future consultation process and project specific information disclosure and document in the ESMP the consultation process conducted, summary of key concerns and agreements, methods/means of consultation.

- Provides a specific description of institutional arrangements, identifying which party is responsible for carrying out the mitigation and monitoring measures (e.g., for operation, supervision, enforcement, monitoring of implementation, remedial action, financing, reporting, and staff training).

- Lay out the grievance mechanisms regarding environmental/social issues and principles for ensuring access to grievance mechanisms including formal grievance redress mechanisms

- Prepare a GBV Action Plan that details the operational measures that will be put in place to assess

and mitigate the risks of gender-based violence, including sexual exploitation and abuse (SEA) and sexual harassment that are project related and how they will be integrated over the life of the project. This includes procedures for preventing and responding to SEA/SH including managing these grievances.

- Prepare a Labour Management Procedures to facilitate the planning and implementation of the project by identifying the main labour requirements and the associated risks and determining the resources necessary to address the project-related labour issues.

- Provide estimates for the budget required for project ESMP implementation.

# 4.Output / Deliverables

- Workplan with timeline within 2 working days of contract signature.

- First draft ESMP report submitted to CARE

- Second Draft ESMP report to CARE & world bank.

- Finalized ESMP report upon completion of the assignment, submitted to CARE and World Bank.

# 5.  Inputs from CARE

- Provide background information and Baseline data (project location, design, operation, or mitigation measures).

- Inputs from MoPSE, Min of Labour and social welfare and CARE meetings

- Rapid Baseline and Gender assessment reports.

# 6.Duration of Consultancy and Proposed Time frame

The consultancy is expected to be conducted and completed within a period of 15 working days including report writing and submission to CARE and World bank.

Activities

Inception meeting

Review background information provided by CARE

Development of ESMP data collection tools

Data collection

Report writing

Submission of first draft report

Submission of second draft report

Submission of final draft

# 7. Profile of the Consultant

A Consultant who:

- An independent specialist with relevant technical expertise, competency, and substantive experience in projects with similar environmental and social risks and impacts.

- Experience supporting and coordinating operational activities, such as household surveys, focus groups, workshops with stakeholders, community consultations, dissemination events.

- Has extensive experience working and navigating the Government line ministries (Ministry of Primary and Secondary Education and Ministry of Labour and social welfare.

- Has excellent conceptual skills

- Can work independently and

- Can meet tight deadlines

8. Applicants to submit the organisational profiles detailing

- Company registration profile

- Workplan and methodology for carrying out the consultancy assignment

- Attach CV of consultant (or of the team members if a consultancy firm applies)

- References

- Applicants to attach samples of relevant work

# 8.Working Arrangements

The consultant will be working under the immediate and direct supervision of the World Bank Environment and Social Development Specialists while also working closely with CIZ. The World Bank and CIZ shall provide the consultant with guidance and shall approve the various stages of the consultancy.

# 9. Covid 19 adaptations

The applicants to adhere to all Covid-19 regulations as required and specified by CIZ and the Government of Zimbabwe in terms of social distancing, transportation of materials, sanitization of surfaces, ventilation of spaces and provision of personal protective gear.

Provide a methodology in consultation with the CIZ team on how they can adapt to COVID-19 regulations in review meetings, collecting data, analysis and validation processes. At a minimum, these should include:

      - Masks for all review and feedback meetings, ensuring everyone knows how to wear them properly (they must cover mouth and nose at all times)

      - Temperatures to be checked daily during review meetings

      - Hand sanitizing

      - No handshakes, especially when providing feedback and during review meetings

      - Conduct feedback and review meetings in outdoor spaces with good air flow

World Bank, Zimbabwe Economic Update Third Edition, 2021

PICES phone survey World Bank staff analysis

PISCES, 2017

Baird, et al, Cash or Condition ? Evidence from a Cash Transfer Experiment, 2011; Baird et al, Relative Effects of Conditional and Unconditional Cash Transfers for Schooling Outcomes in Developing Countries : A Systematic Review, 2013

McIntosh et al, The Impact of Cash Transfers on the Educational Attainment, Sexual Behavior and HIV Status of Adolescent Girls in Malawi, 2007

Banerjee et al, A Multifaceted Program Causes Lasting Progress for the Very Poor : Evidence from Six Countries, 2015

Keetie and Leon-Himmelstine, Graduating out of Poverty Across Generations: Unpacking Children’s Wellbeing Trajectories in Burundi, 2019; Bedoya et al, No Household Left Behind: Afghanistan Targeting the Ultra Poor Evaluation, 2019

Amin et al, Delaying Child Marriage Through Community-Based Skills-Development Programs for Girls : Results from a Randomized Controlled Study from Rural Bangladesh, 2016

https://www.who.int/publications/i/item/9789241549950

See Annex 5

https://friendsofmurambinda.files.wordpress.com/2020/06/fmhannual-report2019-2012532.pdf

Manicaland-Province-2021-ZimVAC-Rural-Livelihoods-Assessment-Report.pdf

Sanitations for Millions’ approach towards menstrual waste management: www.giz.de

Elledge, et al, 2018. Menstrual hygiene management and waste disposal in low- and middle-income countries – A review of the literature in International Journal of environmental research and public health 2018, 15, 2562

Weir, C.S  2015. n The Red: A private economic cost and qualitative analysis of environmental and health implications for five menstrual products.

Available locally through Pad-Up https://wwww.facebook.com/PadUpZim/

https://cpcb.nic.in/uploads/MSW/Final_Sanitary_Waste_Guidelines_15.05.2018.pdf

https://www.care-international.org/files/filesCARE International Safeguarding Policy

https://spherestandards.org

https://cpcb.nic.in/uploads/MSW/Final_Sanitary_Waste_Guidelines_15.05.2018.pdf

See Annex 5 for the detailed Stakeholder Engagement Plan

https://www.ifc.org/wps/wcm/connect/29f5137d-6e17-4660-b1f9-02bf561935e5/Final%2B-%2BGeneral%2BEHS%2BGuidelines.pdf?MOD=AJPERES&CVID=nPtguVM